## Projects_plans
In this tab are the initial forecast of each project launched by Sanitoral
Project ID | Phase | Start Date | Planned_Duration | Planned_Cost | Planned_Delivrable
1 | Phase 1 - Planning | 2018-01-16 | 196 | 50000 | 10
1 | Phase 2 - Initiation | 2018-01-31 | 15 | 100000 | 17
1 | Phase 3 - Implementation | 2018-04-17 | 197 | 150000 | 26
1 | Phase 4 - Manufacturing | 2018-10-10 | 61 | 450000 | 23
2 | Phase 1 - Planning | 2018-01-30 | 16 | 100000 | 6
2 | Phase 2 - Initiation | 2018-04-01 | 109 | 200000 | 27
2 | Phase 3 - Implementation | 2018-06-06 | 146 | 300000 | 18
2 | Phase 4 - Manufacturing | 2018-08-18 | 94 | 900000 | 20
3 | Phase 1 - Planning | 2018-03-03 | 91 | 50000 | 26
3 | Phase 2 - Initiation | 2018-03-25 | 77 | 100000 | 18
3 | Phase 3 - Implementation | 2018-04-28 | 169 | 150000 | 21
3 | Phase 4 - Manufacturing | 2018-10-23 | 61 | 450000 | 8
4 | Phase 1 - Planning | 2018-04-02 | 31 | 50000 | 20
4 | Phase 2 - Initiation | 2018-09-21 | 13 | 100000 | 20
4 | Phase 3 - Implementation | 2018-11-06 | 63 | 150000 | 32
4 | Phase 4 - Manufacturing | 2019-04-02 | 44 | 450000 | 23
5 | Phase 1 - Planning | 2018-01-19 | 11 | 50000 | 3
5 | Phase 2 - Initiation | 2018-02-13 | 167 | 100000 | 21
5 | Phase 3 - Implementation | 2018-03-05 | 197 | 150000 | 22
5 | Phase 4 - Manufacturing | 2018-05-06 | 60 | 450000 | 13
6 | Phase 1 - Planning | 2018-05-02 | 62 | 50000 | 19
6 | Phase 2 - Initiation | 2018-06-28 | 158 | 100000 | 7
6 | Phase 3 - Implementation | 2018-07-18 | 68 | 150000 | 13
6 | Phase 4 - Manufacturing | 2018-10-15 | 30 | 450000 | 4
7 | Phase 1 - Planning | 2018-02-16 | 190 | 100000 | 30
7 | Phase 2 - Initiation | 2018-04-08 | 15 | 200000 | 30
7 | Phase 3 - Implementation | 2018-06-06 | 162 | 300000 | 19
7 | Phase 4 - Manufacturing | 2018-10-27 | 78 | 900000 | 19
8 | Phase 1 - Planning | 2018-04-16 | 48 | 100000 | 28
8 | Phase 2 - Initiation | 2018-07-31 | 179 | 200000 | 5
8 | Phase 3 - Implementation | 2018-10-07 | 7 | 300000 | 10
8 | Phase 4 - Manufacturing | 2018-12-08 | 79 | 900000 | 18
9 | Phase 1 - Planning | 2018-01-27 | 173 | 100000 | 12
9 | Phase 2 - Initiation | 2018-02-28 | 66 | 200000 | 21
9 | Phase 3 - Implementation | 2018-04-21 | 9 | 300000 | 10
9 | Phase 4 - Manufacturing | 2018-06-04 | 98 | 900000 | 3
10 | Phase 1 - Planning | 2018-02-01 | 95 | 33300 | 26
10 | Phase 2 - Initiation | 2018-06-13 | 17 | 66700 | 29
10 | Phase 3 - Implementation | 2018-11-24 | 46 | 100000 | 24
10 | Phase 4 - Manufacturing | 2019-04-04 | 13 | 300000 | 4
11 | Phase 1 - Planning | 2018-04-19 | 55 | 100000 | 4
11 | Phase 2 - Initiation | 2018-08-04 | 6 | 200000 | 13
11 | Phase 3 - Implementation | 2018-08-24 | 107 | 300000 | 17
11 | Phase 4 - Manufacturing | 2019-02-08 | 48 | 900000 | 11
12 | Phase 1 - Planning | 2018-03-10 | 11 | 50000 | 22
12 | Phase 2 - Initiation | 2018-06-04 | 134 | 100000 | 4
12 | Phase 3 - Implementation | 2018-11-04 | 148 | 150000 | 3
12 | Phase 4 - Manufacturing | 2019-03-28 | 148 | 450000 | 22
13 | Phase 1 - Planning | 2018-02-13 | 89 | 50000 | 19
13 | Phase 2 - Initiation | 2018-05-30 | 192 | 100000 | 7
13 | Phase 3 - Implementation | 2018-09-04 | 125 | 150000 | 26
13 | Phase 4 - Manufacturing | 2019-01-21 | 176 | 450000 | 22
14 | Phase 1 - Planning | 2018-04-13 | 191 | 50000 | 9
14 | Phase 2 - Initiation | 2018-04-28 | 131 | 100000 | 31
14 | Phase 3 - Implementation | 2018-05-02 | 1 | 150000 | 1
14 | Phase 4 - Manufacturing | 2018-09-24 | 136 | 450000 | 20
15 | Phase 1 - Planning | 2018-01-01 | 166 | 33300 | 22
15 | Phase 2 - Initiation | 2018-01-19 | 159 | 66700 | 25
15 | Phase 3 - Implementation | 2018-07-09 | 26 | 100000 | 32
15 | Phase 4 - Manufacturing | 2018-09-28 | 110 | 300000 | 14
16 | Phase 1 - Planning | 2018-02-07 | 30 | 33300 | 6
16 | Phase 2 - Initiation | 2018-05-21 | 101 | 66700 | 7
16 | Phase 3 - Implementation | 2018-09-13 | 152 | 100000 | 7
16 | Phase 4 - Manufacturing | 2018-09-23 | 21 | 300000 | 6
17 | Phase 1 - Planning | 2018-01-07 | 140 | 100000 | 26
17 | Phase 2 - Initiation | 2018-04-14 | 174 | 200000 | 13
17 | Phase 3 - Implementation | 2018-06-20 | 110 | 300000 | 28
17 | Phase 4 - Manufacturing | 2018-11-14 | 72 | 900000 | 12
18 | Phase 1 - Planning | 2018-04-04 | 89 | 33300 | 8
18 | Phase 2 - Initiation | 2018-06-07 | 178 | 66700 | 15
18 | Phase 3 - Implementation | 2018-08-11 | 34 | 100000 | 13
18 | Phase 4 - Manufacturing | 2018-09-21 | 119 | 300000 | 29
19 | Phase 1 - Planning | 2018-03-17 | 186 | 100000 | 29
19 | Phase 2 - Initiation | 2018-04-05 | 115 | 200000 | 24
19 | Phase 3 - Implementation | 2018-09-07 | 184 | 300000 | 17
19 | Phase 4 - Manufacturing | 2018-12-26 | 145 | 900000 | 21
20 | Phase 1 - Planning | 2018-01-25 | 125 | 50000 | 8
20 | Phase 2 - Initiation | 2018-02-15 | 117 | 100000 | 23
20 | Phase 3 - Implementation | 2018-05-10 | 54 | 150000 | 24
20 | Phase 4 - Manufacturing | 2018-08-17 | 120 | 450000 | 30
21 | Phase 1 - Planning | 2018-04-13 | 49 | 50000 | 8
21 | Phase 2 - Initiation | 2018-06-06 | 60 | 100000 | 20
21 | Phase 3 - Implementation | 2018-11-23 | 151 | 150000 | 24
21 | Phase 4 - Manufacturing | 2019-03-09 | 177 | 450000 | 12
22 | Phase 1 - Planning | 2018-03-06 | 175 | 50000 | 5
22 | Phase 2 - Initiation | 2018-04-05 | 149 | 100000 | 3
22 | Phase 3 - Implementation | 2018-08-08 | 198 | 150000 | 7
22 | Phase 4 - Manufacturing | 2018-10-01 | 109 | 450000 | 27
23 | Phase 1 - Planning | 2018-04-26 | 151 | 100000 | 6
23 | Phase 2 - Initiation | 2018-06-22 | 16 | 200000 | 26
23 | Phase 3 - Implementation | 2018-09-09 | 67 | 300000 | 3
23 | Phase 4 - Manufacturing | 2019-01-22 | 14 | 900000 | 21
24 | Phase 1 - Planning | 2018-03-03 | 165 | 50000 | 13
24 | Phase 2 - Initiation | 2018-04-21 | 125 | 100000 | 21
24 | Phase 3 - Implementation | 2018-08-31 | 132 | 150000 | 21
24 | Phase 4 - Manufacturing | 2018-10-24 | 189 | 450000 | 23
25 | Phase 1 - Planning | 2018-02-05 | 20 | 33300 | 11
25 | Phase 2 - Initiation | 2018-03-07 | 188 | 66700 | 11
25 | Phase 3 - Implementation | 2018-03-15 | 102 | 100000 | 7
25 | Phase 4 - Manufacturing | 2018-05-17 | 105 | 300000 | 6
26 | Phase 1 - Planning | 2018-05-23 | 76 | 100000 | 31
26 | Phase 2 - Initiation | 2018-10-18 | 28 | 200000 | 3
26 | Phase 3 - Implementation | 2019-01-08 | 128 | 300000 | 27
26 | Phase 4 - Manufacturing | 2019-01-20 | 3 | 900000 | 6
27 | Phase 1 - Planning | 2018-02-19 | 60 | 50000 | 23
27 | Phase 2 - Initiation | 2018-06-13 | 199 | 100000 | 12
27 | Phase 3 - Implementation | 2018-11-11 | 57 | 150000 | 20
27 | Phase 4 - Manufacturing | 2018-12-09 | 125 | 450000 | 18
28 | Phase 1 - Planning | 2018-01-24 | 21 | 100000 | 14
28 | Phase 2 - Initiation | 2018-06-08 | 94 | 200000 | 7
28 | Phase 3 - Implementation | 2018-07-29 | 128 | 300000 | 17
28 | Phase 4 - Manufacturing | 2018-08-26 | 91 | 900000 | 32
29 | Phase 1 - Planning | 2018-03-08 | 7 | 50000 | 7
29 | Phase 2 - Initiation | 2018-07-26 | 80 | 100000 | 5
29 | Phase 3 - Implementation | 2018-09-07 | 117 | 150000 | 5
29 | Phase 4 - Manufacturing | 2019-01-01 | 5 | 450000 | 16
30 | Phase 1 - Planning | 2018-01-07 | 165 | 100000 | 20
30 | Phase 2 - Initiation | 2018-02-11 | 182 | 200000 | 11
30 | Phase 3 - Implementation | 2018-03-01 | 17 | 300000 | 8
30 | Phase 4 - Manufacturing | 2018-03-31 | 149 | 900000 | 23
31 | Phase 1 - Planning | 2018-04-12 | 26 | 100000 | 4
31 | Phase 2 - Initiation | 2018-06-13 | 76 | 200000 | 20
31 | Phase 3 - Implementation | 2018-11-10 | 94 | 300000 | 17
31 | Phase 4 - Manufacturing | 2019-01-03 | 86 | 900000 | 23
32 | Phase 1 - Planning | 2018-02-28 | 107 | 50000 | 10
32 | Phase 2 - Initiation | 2018-03-09 | 76 | 100000 | 5
32 | Phase 3 - Implementation | 2018-04-03 | 134 | 150000 | 25
32 | Phase 4 - Manufacturing | 2018-07-20 | 34 | 450000 | 9
33 | Phase 1 - Planning | 2018-03-31 | 53 | 50000 | 12
33 | Phase 2 - Initiation | 2018-06-04 | 87 | 100000 | 21
33 | Phase 3 - Implementation | 2018-06-16 | 45 | 150000 | 4
33 | Phase 4 - Manufacturing | 2018-10-04 | 121 | 450000 | 11
34 | Phase 1 - Planning | 2018-05-26 | 109 | 100000 | 12
34 | Phase 2 - Initiation | 2018-07-03 | 153 | 200000 | 23
34 | Phase 3 - Implementation | 2018-07-06 | 165 | 300000 | 15
34 | Phase 4 - Manufacturing | 2018-11-15 | 181 | 900000 | 24
35 | Phase 1 - Planning | 2018-03-02 | 25 | 100000 | 27
35 | Phase 2 - Initiation | 2018-04-01 | 195 | 200000 | 17
35 | Phase 3 - Implementation | 2018-07-06 | 54 | 300000 | 11
35 | Phase 4 - Manufacturing | 2018-09-21 | 79 | 900000 | 26
36 | Phase 1 - Planning | 2018-02-25 | 54 | 50000 | 8
36 | Phase 2 - Initiation | 2018-07-13 | 66 | 100000 | 3
36 | Phase 3 - Implementation | 2018-12-17 | 63 | 150000 | 25
36 | Phase 4 - Manufacturing | 2019-05-10 | 176 | 450000 | 26
37 | Phase 1 - Planning | 2018-01-24 | 19 | 50000 | 7
37 | Phase 2 - Initiation | 2018-06-01 | 110 | 100000 | 11
37 | Phase 3 - Implementation | 2018-08-15 | 137 | 150000 | 32
37 | Phase 4 - Manufacturing | 2018-11-15 | 119 | 450000 | 8
38 | Phase 1 - Planning | 2018-04-22 | 135 | 50000 | 14
38 | Phase 2 - Initiation | 2018-05-30 | 48 | 100000 | 26
38 | Phase 3 - Implementation | 2018-08-22 | 171 | 150000 | 23
38 | Phase 4 - Manufacturing | 2019-01-04 | 47 | 450000 | 6
39 | Phase 1 - Planning | 2018-02-16 | 38 | 100000 | 31
39 | Phase 2 - Initiation | 2018-07-26 | 173 | 200000 | 19
39 | Phase 3 - Implementation | 2018-12-21 | 21 | 300000 | 11
39 | Phase 4 - Manufacturing | 2019-04-21 | 162 | 900000 | 9
40 | Phase 1 - Planning | 2018-04-28 | 142 | 33300 | 27
40 | Phase 2 - Initiation | 2018-05-19 | 91 | 66700 | 18
40 | Phase 3 - Implementation | 2018-09-17 | 175 | 100000 | 20
40 | Phase 4 - Manufacturing | 2018-12-16 | 54 | 300000 | 15
41 | Phase 1 - Planning | 2018-05-05 | 53 | 100000 | 29
41 | Phase 2 - Initiation | 2018-07-28 | 89 | 200000 | 32
41 | Phase 3 - Implementation | 2018-08-18 | 74 | 300000 | 23
41 | Phase 4 - Manufacturing | 2018-08-22 | 140 | 900000 | 6
42 | Phase 1 - Planning | 2018-05-27 | 194 | 50000 | 9
42 | Phase 2 - Initiation | 2018-08-28 | 183 | 100000 | 29
42 | Phase 3 - Implementation | 2018-11-22 | 166 | 150000 | 13
42 | Phase 4 - Manufacturing | 2019-01-24 | 33 | 450000 | 22
43 | Phase 1 - Planning | 2018-02-24 | 4 | 100000 | 14
43 | Phase 2 - Initiation | 2018-05-18 | 151 | 200000 | 7
43 | Phase 3 - Implementation | 2018-08-18 | 187 | 300000 | 7
43 | Phase 4 - Manufacturing | 2018-12-25 | 81 | 900000 | 6
44 | Phase 1 - Planning | 2018-02-27 | 117 | 50000 | 8
44 | Phase 2 - Initiation | 2018-04-07 | 126 | 100000 | 6
44 | Phase 3 - Implementation | 2018-04-19 | 71 | 150000 | 10
44 | Phase 4 - Manufacturing | 2018-10-02 | 113 | 450000 | 23
45 | Phase 1 - Planning | 2018-04-25 | 139 | 33300 | 13
45 | Phase 2 - Initiation | 2018-09-26 | 193 | 66700 | 10
45 | Phase 3 - Implementation | 2018-11-25 | 56 | 100000 | 28
45 | Phase 4 - Manufacturing | 2019-01-15 | 149 | 300000 | 28
46 | Phase 1 - Planning | 2018-04-20 | 10 | 50000 | 17
46 | Phase 2 - Initiation | 2018-08-27 | 60 | 100000 | 19
46 | Phase 3 - Implementation | 2019-02-19 | 184 | 150000 | 31
46 | Phase 4 - Manufacturing | 2019-06-05 | 200 | 450000 | 7
47 | Phase 1 - Planning | 2018-01-31 | 54 | 33300 | 32
47 | Phase 2 - Initiation | 2018-03-12 | 152 | 66700 | 25
47 | Phase 3 - Implementation | 2018-09-08 | 90 | 100000 | 28
47 | Phase 4 - Manufacturing | 2018-12-04 | 49 | 300000 | 9
48 | Phase 1 - Planning | 2018-04-08 | 66 | 100000 | 24
48 | Phase 2 - Initiation | 2018-05-05 | 110 | 200000 | 27
48 | Phase 3 - Implementation | 2018-08-03 | 178 | 300000 | 11
48 | Phase 4 - Manufacturing | 2018-08-22 | 167 | 900000 | 32
49 | Phase 1 - Planning | 2018-04-19 | 30 | 50000 | 32
49 | Phase 2 - Initiation | 2018-10-08 | 84 | 100000 | 27
49 | Phase 3 - Implementation | 2018-11-18 | 186 | 150000 | 31
49 | Phase 4 - Manufacturing | 2019-01-27 | 86 | 450000 | 24
50 | Phase 1 - Planning | 2018-05-27 | 158 | 50000 | 12
50 | Phase 2 - Initiation | 2018-07-28 | 136 | 100000 | 25
50 | Phase 3 - Implementation | 2018-09-22 | 121 | 150000 | 19
50 | Phase 4 - Manufacturing | 2018-11-01 | 129 | 450000 | 10
51 | Phase 1 - Planning | 2018-02-05 | 129 | 100000 | 12
51 | Phase 2 - Initiation | 2018-05-24 | 138 | 200000 | 6
51 | Phase 3 - Implementation | 2018-07-06 | 31 | 300000 | 7
51 | Phase 4 - Manufacturing | 2018-12-11 | 76 | 900000 | 28
52 | Phase A - Initiation | 2020-03-12 | 139 | 700 | 26
52 | Phase B - Preparation | 2020-06-29 | 157 | 16100 | 24
52 | Phase C - Development | 2020-08-04 | 9 | 21000 | 23
52 | Phase D - Testing | 2020-12-19 | 48 | 5600 | 25
52 | Phase E - Deployment | 2021-03-14 | 161 | 115000 | 5
52 | Phase F - Post-deployment | 2021-07-06 | 26 | 2800 | 7
53 | Phase A - Initiation | 2020-04-23 | 38 | 700 | 10
53 | Phase B - Preparation | 2020-06-06 | 61 | 16100 | 31
53 | Phase C - Development | 2020-10-11 | 39 | 21000 | 8
53 | Phase D - Testing | 2020-12-30 | 15 | 5600 | 20
53 | Phase E - Deployment | 2021-02-14 | 124 | 80000 | 28
53 | Phase F - Post-deployment | 2021-06-21 | 111 | 2800 | 25
54 | Phase A - Initiation | 2020-05-20 | 173 | 700 | 10
54 | Phase B - Preparation | 2020-06-17 | 29 | 16100 | 30
54 | Phase C - Development | 2020-11-16 | 64 | 21000 | 4
54 | Phase D - Testing | 2021-01-24 | 173 | 5600 | 17
54 | Phase E - Deployment | 2021-06-25 | 52 | 50000 | 12
54 | Phase F - Post-deployment | 2021-09-12 | 184 | 2800 | 20
55 | Phase A - Initiation | 2020-01-15 | 68 | 700 | 29
55 | Phase B - Preparation | 2020-02-28 | 161 | 16100 | 7
55 | Phase C - Development | 2020-07-17 | 66 | 21000 | 9
55 | Phase D - Testing | 2020-08-17 | 153 | 5600 | 7
55 | Phase E - Deployment | 2020-10-20 | 83 | 58000 | 26
55 | Phase F - Post-deployment | 2021-01-17 | 19 | 2800 | 6
56 | Phase A - Initiation | 2020-02-07 | 154 | 700 | 8
56 | Phase B - Preparation | 2020-02-15 | 47 | 16100 | 32
56 | Phase C - Development | 2020-05-28 | 95 | 21000 | 4
56 | Phase D - Testing | 2020-09-21 | 12 | 5600 | 17
56 | Phase E - Deployment | 2020-12-23 | 160 | 33000 | 4
56 | Phase F - Post-deployment | 2021-06-14 | 124 | 2800 | 5
57 | Phase A - Initiation | 2020-05-04 | 157 | 700 | 13
57 | Phase B - Preparation | 2020-10-16 | 117 | 16100 | 7
57 | Phase C - Development | 2021-03-30 | 127 | 21000 | 13
57 | Phase D - Testing | 2021-05-02 | 25 | 5600 | 9
57 | Phase E - Deployment | 2021-09-08 | 65 | 32000 | 26
57 | Phase F - Post-deployment | 2021-11-03 | 200 | 2800 | 5
58 | Phase A - Initiation | 2020-04-07 | 33 | 700 | 21
58 | Phase B - Preparation | 2020-06-21 | 73 | 16100 | 24
58 | Phase C - Development | 2020-10-02 | 187 | 21000 | 13
58 | Phase D - Testing | 2021-02-26 | 153 | 5600 | 25
58 | Phase E - Deployment | 2021-05-13 | 36 | 73000 | 4
58 | Phase F - Post-deployment | 2021-09-26 | 183 | 2800 | 30
59 | Phase A - Initiation | 2020-03-07 | 18 | 400 | 6
59 | Phase B - Preparation | 2020-05-29 | 42 | 8100 | 5
59 | Phase C - Development | 2020-06-30 | 42 | 10500 | 26
59 | Phase D - Testing | 2020-11-15 | 121 | 2800 | 14
59 | Phase E - Deployment | 2021-03-23 | 85 | 59000 | 30
59 | Phase F - Post-deployment | 2021-07-25 | 7 | 1400 | 11
60 | Phase A - Initiation | 2020-03-03 | 177 | 400 | 14
60 | Phase B - Preparation | 2020-05-27 | 30 | 8100 | 10
60 | Phase C - Development | 2020-11-01 | 80 | 10500 | 17
60 | Phase D - Testing | 2021-04-08 | 169 | 2800 | 8
60 | Phase E - Deployment | 2021-09-30 | 94 | 43000 | 29
60 | Phase F - Post-deployment | 2021-10-28 | 151 | 1400 | 29
61 | Phase A - Initiation | 2020-01-05 | 122 | 700 | 27
61 | Phase B - Preparation | 2020-02-04 | 65 | 16100 | 8
61 | Phase C - Development | 2020-07-03 | 109 | 21000 | 23
61 | Phase D - Testing | 2020-07-07 | 1 | 5600 | 2
61 | Phase E - Deployment | 2020-07-13 | 99 | 47000 | 12
61 | Phase F - Post-deployment | 2020-09-18 | 82 | 2800 | 27
62 | Phase A - Initiation | 2020-01-30 | 18 | 700 | 5
62 | Phase B - Preparation | 2020-03-06 | 94 | 16100 | 6
62 | Phase C - Development | 2020-03-09 | 151 | 21000 | 7
62 | Phase D - Testing | 2020-05-25 | 106 | 5600 | 15
62 | Phase E - Deployment | 2020-07-21 | 31 | 54000 | 18
62 | Phase F - Post-deployment | 2020-10-09 | 31 | 2800 | 12
63 | Phase A - Initiation | 2020-03-07 | 60 | 700 | 19
63 | Phase B - Preparation | 2020-04-04 | 4 | 16100 | 7
63 | Phase C - Development | 2020-08-05 | 153 | 21000 | 17
63 | Phase D - Testing | 2020-12-26 | 85 | 5600 | 15
63 | Phase E - Deployment | 2021-01-24 | 176 | 32000 | 10
63 | Phase F - Post-deployment | 2021-03-02 | 104 | 2800 | 15
64 | Phase A - Initiation | 2020-01-17 | 63 | 400 | 4
64 | Phase B - Preparation | 2020-03-29 | 16 | 8100 | 25
64 | Phase C - Development | 2020-08-03 | 198 | 10500 | 24
64 | Phase D - Testing | 2020-08-27 | 176 | 2800 | 28
64 | Phase E - Deployment | 2020-12-24 | 166 | 67000 | 23
64 | Phase F - Post-deployment | 2021-06-06 | 193 | 1400 | 27
65 | Phase A - Initiation | 2020-05-24 | 104 | 400 | 14
65 | Phase B - Preparation | 2020-09-08 | 173 | 8100 | 27
65 | Phase C - Development | 2021-01-09 | 8 | 10500 | 10
65 | Phase D - Testing | 2021-04-01 | 14 | 2800 | 10
65 | Phase E - Deployment | 2021-05-27 | 29 | 25000 | 25
65 | Phase F - Post-deployment | 2021-10-27 | 114 | 1400 | 19
66 | Phase A - Initiation | 2020-01-02 | 20 | 700 | 21
66 | Phase B - Preparation | 2020-05-13 | 160 | 16100 | 13
66 | Phase C - Development | 2020-07-09 | 79 | 21000 | 30
66 | Phase D - Testing | 2020-12-16 | 129 | 5600 | 24
66 | Phase E - Deployment | 2021-05-12 | 135 | 44000 | 18
66 | Phase F - Post-deployment | 2021-09-29 | 195 | 2800 | 29
67 | Phase A - Initiation | 2020-01-05 | 14 | 400 | 32
67 | Phase B - Preparation | 2020-01-12 | 69 | 8100 | 17
67 | Phase C - Development | 2020-02-16 | 144 | 10500 | 16
67 | Phase D - Testing | 2020-04-20 | 140 | 2800 | 24
67 | Phase E - Deployment | 2020-07-25 | 135 | 75000 | 27
67 | Phase F - Post-deployment | 2020-09-11 | 79 | 1400 | 7
68 | Phase A - Initiation | 2020-01-23 | 141 | 400 | 4
68 | Phase B - Preparation | 2020-07-01 | 164 | 8100 | 13
68 | Phase C - Development | 2020-07-19 | 70 | 10500 | 10
68 | Phase D - Testing | 2020-09-11 | 132 | 2800 | 4
68 | Phase E - Deployment | 2020-11-16 | 92 | 36000 | 3
68 | Phase F - Post-deployment | 2021-03-15 | 109 | 1400 | 22
69 | Phase A - Initiation | 2020-05-31 | 197 | 700 | 14
69 | Phase B - Preparation | 2020-08-20 | 193 | 16100 | 28
69 | Phase C - Development | 2021-01-01 | 58 | 21000 | 4
69 | Phase D - Testing | 2021-06-07 | 91 | 5600 | 16
69 | Phase E - Deployment | 2021-08-26 | 27 | 79000 | 25
69 | Phase F - Post-deployment | 2022-02-13 | 187 | 2800 | 31
70 | Phase A - Initiation | 2020-05-11 | 134 | 400 | 19
70 | Phase B - Preparation | 2020-08-17 | 191 | 8100 | 7
70 | Phase C - Development | 2020-12-25 | 35 | 10500 | 18
70 | Phase D - Testing | 2021-02-05 | 1 | 2800 | 3
70 | Phase E - Deployment | 2021-05-30 | 164 | 83000 | 6
70 | Phase F - Post-deployment | 2021-11-17 | 60 | 1400 | 29
71 | Phase A - Initiation | 2020-03-11 | 135 | 400 | 30
71 | Phase B - Preparation | 2020-05-29 | 152 | 8100 | 18
71 | Phase C - Development | 2020-11-18 | 14 | 10500 | 30
71 | Phase D - Testing | 2020-12-28 | 125 | 2800 | 14
71 | Phase E - Deployment | 2021-02-10 | 95 | 46000 | 20
71 | Phase F - Post-deployment | 2021-06-13 | 134 | 1400 | 14
72 | Phase A - Initiation | 2020-05-11 | 193 | 400 | 32
72 | Phase B - Preparation | 2020-05-26 | 113 | 8100 | 24
72 | Phase C - Development | 2020-06-01 | 86 | 10500 | 21
72 | Phase D - Testing | 2020-08-20 | 75 | 2800 | 9
72 | Phase E - Deployment | 2020-10-23 | 178 | 66000 | 31
72 | Phase F - Post-deployment | 2020-12-27 | 3 | 1400 | 3
73 | Phase A - Initiation | 2020-05-05 | 127 | 400 | 22
73 | Phase B - Preparation | 2020-07-30 | 52 | 8100 | 8
73 | Phase C - Development | 2021-01-19 | 37 | 10500 | 4
73 | Phase D - Testing | 2021-05-09 | 52 | 2800 | 13
73 | Phase E - Deployment | 2021-07-21 | 53 | 40000 | 7
73 | Phase F - Post-deployment | 2021-08-09 | 89 | 1400 | 16
74 | Phase A - Initiation | 2020-01-14 | 158 | 400 | 27
74 | Phase B - Preparation | 2020-05-23 | 123 | 8100 | 10
74 | Phase C - Development | 2020-07-20 | 181 | 10500 | 12
74 | Phase D - Testing | 2020-08-22 | 154 | 2800 | 7
74 | Phase E - Deployment | 2020-12-17 | 153 | 51000 | 8
74 | Phase F - Post-deployment | 2021-02-15 | 172 | 1400 | 32
75 | Phase A - Initiation | 2020-03-20 | 8 | 700 | 4
75 | Phase B - Preparation | 2020-06-12 | 122 | 16100 | 32
75 | Phase C - Development | 2020-08-07 | 132 | 21000 | 22
75 | Phase D - Testing | 2020-12-09 | 104 | 5600 | 29
75 | Phase E - Deployment | 2021-02-20 | 110 | 103000 | 8
75 | Phase F - Post-deployment | 2021-05-07 | 69 | 2800 | 30
76 | Phase A - Initiation | 2020-03-23 | 31 | 400 | 14
76 | Phase B - Preparation | 2020-09-14 | 196 | 8100 | 26
76 | Phase C - Development | 2021-01-12 | 145 | 10500 | 17
76 | Phase D - Testing | 2021-05-29 | 44 | 2800 | 8
76 | Phase E - Deployment | 2021-10-01 | 61 | 53000 | 14
76 | Phase F - Post-deployment | 2022-02-06 | 78 | 1400 | 30
77 | Phase A - Initiation | 2020-03-27 | 11 | 400 | 5
77 | Phase B - Preparation | 2020-07-22 | 134 | 8100 | 23
77 | Phase C - Development | 2020-08-20 | 188 | 10500 | 15
77 | Phase D - Testing | 2020-12-30 | 99 | 2800 | 18
77 | Phase E - Deployment | 2021-06-08 | 166 | 33000 | 20
77 | Phase F - Post-deployment | 2021-09-18 | 189 | 1400 | 11
78 | Phase A - Initiation | 2020-05-18 | 164 | 400 | 28
78 | Phase B - Preparation | 2020-10-05 | 101 | 8100 | 15
78 | Phase C - Development | 2021-02-10 | 38 | 10500 | 21
78 | Phase D - Testing | 2021-03-08 | 26 | 2800 | 15
78 | Phase E - Deployment | 2021-04-16 | 31 | 37000 | 8
78 | Phase F - Post-deployment | 2021-10-11 | 99 | 1400 | 11
79 | Phase A - Initiation | 2020-02-05 | 127 | 700 | 14
79 | Phase B - Preparation | 2020-05-25 | 126 | 16100 | 30
79 | Phase C - Development | 2020-10-28 | 184 | 21000 | 20
79 | Phase D - Testing | 2021-01-08 | 123 | 5600 | 15
79 | Phase E - Deployment | 2021-02-26 | 122 | 66000 | 3
79 | Phase F - Post-deployment | 2021-05-03 | 172 | 2800 | 23
80 | Phase A - Initiation | 2020-02-23 | 159 | 700 | 6
80 | Phase B - Preparation | 2020-04-02 | 186 | 16100 | 15
80 | Phase C - Development | 2020-05-05 | 198 | 21000 | 12
80 | Phase D - Testing | 2020-09-23 | 101 | 5600 | 32
80 | Phase E - Deployment | 2021-03-12 | 170 | 71000 | 13
80 | Phase F - Post-deployment | 2021-05-21 | 131 | 2800 | 4
81 | Phase A - Initiation | 2020-05-28 | 113 | 700 | 13
81 | Phase B - Preparation | 2020-10-13 | 48 | 16100 | 19
81 | Phase C - Development | 2020-12-02 | 1 | 21000 | 1
81 | Phase D - Testing | 2021-05-03 | 53 | 5600 | 30
81 | Phase E - Deployment | 2021-10-13 | 168 | 123000 | 27
81 | Phase F - Post-deployment | 2021-10-25 | 185 | 2800 | 31
82 | Phase A - Initiation | 2020-04-20 | 63 | 700 | 19
82 | Phase B - Preparation | 2020-06-24 | 174 | 16100 | 31
82 | Phase C - Development | 2020-07-07 | 20 | 21000 | 29
82 | Phase D - Testing | 2020-11-18 | 102 | 5600 | 5
82 | Phase E - Deployment | 2021-02-28 | 58 | 66000 | 23
82 | Phase F - Post-deployment | 2021-04-05 | 194 | 2800 | 28
83 | Phase A - Initiation | 2020-03-07 | 41 | 200 | 20
83 | Phase B - Preparation | 2020-07-14 | 124 | 5400 | 18
83 | Phase C - Development | 2020-07-24 | 185 | 7000 | 21
83 | Phase D - Testing | 2020-09-02 | 112 | 1900 | 29
83 | Phase E - Deployment | 2021-01-01 | 81 | 62000 | 22
83 | Phase F - Post-deployment | 2021-06-05 | 174 | 900 | 7
84 | Phase A - Initiation | 2020-01-27 | 191 | 200 | 7
84 | Phase B - Preparation | 2020-03-31 | 46 | 5400 | 8
84 | Phase C - Development | 2020-08-30 | 109 | 7000 | 31
84 | Phase D - Testing | 2021-01-15 | 30 | 1900 | 9
84 | Phase E - Deployment | 2021-07-12 | 5 | 59000 | 17
84 | Phase F - Post-deployment | 2021-11-11 | 115 | 900 | 12
85 | Phase A - Initiation | 2020-03-14 | 187 | 400 | 21
85 | Phase B - Preparation | 2020-06-04 | 76 | 8100 | 4
85 | Phase C - Development | 2020-10-17 | 31 | 10500 | 27
85 | Phase D - Testing | 2021-02-12 | 123 | 2800 | 29
85 | Phase E - Deployment | 2021-07-07 | 109 | 70000 | 25
85 | Phase F - Post-deployment | 2021-11-19 | 197 | 1400 | 26
86 | Phase A - Initiation | 2020-01-13 | 36 | 200 | 18
86 | Phase B - Preparation | 2020-03-29 | 193 | 5400 | 10
86 | Phase C - Development | 2020-08-04 | 109 | 7000 | 30
86 | Phase D - Testing | 2020-12-07 | 76 | 1900 | 8
86 | Phase E - Deployment | 2021-01-29 | 92 | 108000 | 6
86 | Phase F - Post-deployment | 2021-07-01 | 139 | 900 | 3
87 | Phase A - Initiation | 2020-03-08 | 112 | 200 | 4
87 | Phase B - Preparation | 2020-05-30 | 50 | 5400 | 13
87 | Phase C - Development | 2020-09-26 | 96 | 7000 | 14
87 | Phase D - Testing | 2021-01-20 | 79 | 1900 | 17
87 | Phase E - Deployment | 2021-06-09 | 183 | 69000 | 16
87 | Phase F - Post-deployment | 2021-12-04 | 148 | 900 | 15
88 | Phase A - Initiation | 2020-05-02 | 92 | 200 | 30
88 | Phase B - Preparation | 2020-10-11 | 75 | 5400 | 30
88 | Phase C - Development | 2021-01-22 | 96 | 7000 | 7
88 | Phase D - Testing | 2021-03-21 | 108 | 1900 | 7
88 | Phase E - Deployment | 2021-08-14 | 77 | 61000 | 15
88 | Phase F - Post-deployment | 2021-08-17 | 57 | 900 | 22
89 | Phase A - Initiation | 2020-03-09 | 20 | 200 | 19
89 | Phase B - Preparation | 2020-08-30 | 149 | 5400 | 10
89 | Phase C - Development | 2021-02-16 | 103 | 7000 | 23
89 | Phase D - Testing | 2021-03-10 | 4 | 1900 | 18
89 | Phase E - Deployment | 2021-06-11 | 152 | 123000 | 16
89 | Phase F - Post-deployment | 2021-09-14 | 109 | 900 | 12
90 | Phase A - Initiation | 2020-03-10 | 2 | 200 | 3
90 | Phase B - Preparation | 2020-06-04 | 17 | 5400 | 4
90 | Phase C - Development | 2020-11-27 | 52 | 7000 | 9
90 | Phase D - Testing | 2021-03-01 | 60 | 1900 | 21
90 | Phase E - Deployment | 2021-08-03 | 182 | 44000 | 29
90 | Phase F - Post-deployment | 2021-09-23 | 96 | 900 | 26
91 | Phase A - Initiation | 2020-03-30 | 54 | 200 | 7
91 | Phase B - Preparation | 2020-05-15 | 183 | 5400 | 25
91 | Phase C - Development | 2020-09-16 | 129 | 7000 | 18
91 | Phase D - Testing | 2020-12-17 | 35 | 1900 | 25
91 | Phase E - Deployment | 2021-03-04 | 144 | 89000 | 32
91 | Phase F - Post-deployment | 2021-03-22 | 72 | 900 | 19
92 | Phase A - Initiation | 2020-04-19 | 77 | 400 | 13
92 | Phase B - Preparation | 2020-07-24 | 45 | 8100 | 24
92 | Phase C - Development | 2020-12-04 | 191 | 10500 | 7
92 | Phase D - Testing | 2021-05-16 | 102 | 2800 | 30
92 | Phase E - Deployment | 2021-09-06 | 127 | 42000 | 17
92 | Phase F - Post-deployment | 2021-10-15 | 126 | 1400 | 16
93 | Phase A - Initiation | 2020-03-22 | 41 | 400 | 8
93 | Phase B - Preparation | 2020-07-25 | 188 | 8100 | 27
93 | Phase C - Development | 2020-11-06 | 45 | 10500 | 10
93 | Phase D - Testing | 2021-01-05 | 159 | 2800 | 14
93 | Phase E - Deployment | 2021-06-13 | 104 | 51000 | 27
93 | Phase F - Post-deployment | 2021-10-23 | 28 | 1400 | 11
94 | Phase A - Initiation | 2020-03-02 | 121 | 700 | 23
94 | Phase B - Preparation | 2020-05-08 | 16 | 16100 | 30
94 | Phase C - Development | 2020-06-22 | 110 | 21000 | 29
94 | Phase D - Testing | 2020-12-13 | 132 | 5600 | 10
94 | Phase E - Deployment | 2021-01-12 | 83 | 45000 | 7
94 | Phase F - Post-deployment | 2021-01-22 | 46 | 2800 | 6
95 | Phase A - Initiation | 2020-04-05 | 28 | 400 | 20
95 | Phase B - Preparation | 2020-07-05 | 49 | 8100 | 30
95 | Phase C - Development | 2020-11-09 | 187 | 10500 | 29
95 | Phase D - Testing | 2020-12-24 | 93 | 2800 | 19
95 | Phase E - Deployment | 2021-03-18 | 96 | 86000 | 19
95 | Phase F - Post-deployment | 2021-08-29 | 175 | 1400 | 16
96 | Phase A - Initiation | 2020-05-26 | 15 | 400 | 23
96 | Phase B - Preparation | 2020-08-07 | 75 | 8100 | 14
96 | Phase C - Development | 2020-10-14 | 161 | 10500 | 15
96 | Phase D - Testing | 2021-02-05 | 193 | 2800 | 29
96 | Phase E - Deployment | 2021-05-15 | 62 | 123000 | 24
96 | Phase F - Post-deployment | 2021-06-08 | 80 | 1400 | 8
97 | Phase A - Initiation | 2020-02-05 | 86 | 400 | 3
97 | Phase B - Preparation | 2020-04-06 | 150 | 8100 | 29
97 | Phase C - Development | 2020-04-12 | 125 | 10500 | 9
97 | Phase D - Testing | 2020-06-27 | 53 | 2800 | 6
97 | Phase E - Deployment | 2020-09-15 | 134 | 47000 | 26
97 | Phase F - Post-deployment | 2021-02-04 | 32 | 1400 | 8
98 | Phase A - Initiation | 2020-02-14 | 40 | 400 | 28
98 | Phase B - Preparation | 2020-08-05 | 116 | 8100 | 27
98 | Phase C - Development | 2020-09-11 | 147 | 10500 | 17
98 | Phase D - Testing | 2020-12-20 | 21 | 2800 | 8
98 | Phase E - Deployment | 2021-02-08 | 118 | 32000 | 13
98 | Phase F - Post-deployment | 2021-06-27 | 143 | 1400 | 19
99 | Phase A - Initiation | 2020-04-15 | 64 | 400 | 24
99 | Phase B - Preparation | 2020-07-07 | 32 | 8100 | 14
99 | Phase C - Development | 2020-07-23 | 130 | 10500 | 11
99 | Phase D - Testing | 2020-09-15 | 102 | 2800 | 31
99 | Phase E - Deployment | 2020-10-21 | 134 | 53000 | 22
99 | Phase F - Post-deployment | 2020-10-28 | 34 | 1400 | 5
100 | Phase A - Initiation | 2020-05-21 | 115 | 400 | 18
100 | Phase B - Preparation | 2020-06-22 | 190 | 8100 | 16
100 | Phase C - Development | 2020-07-07 | 92 | 10500 | 21
100 | Phase D - Testing | 2020-12-21 | 123 | 2800 | 5
100 | Phase E - Deployment | 2021-05-19 | 54 | 68000 | 17
100 | Phase F - Post-deployment | 2021-05-28 | 32 | 1400 | 18
101 | Phase A - Initiation | 2020-01-16 | 121 | 700 | 25
101 | Phase B - Preparation | 2020-03-26 | 109 | 16100 | 30
101 | Phase C - Development | 2020-06-05 | 175 | 21000 | 20
101 | Phase D - Testing | 2020-11-27 | 68 | 5600 | 6
101 | Phase E - Deployment | 2021-02-21 | 2 | 75000 | 5
101 | Phase F - Post-deployment | 2021-04-26 | 64 | 2800 | 10
102 | Phase A - Initiation | 2020-03-20 | 155 | 400 | 9
102 | Phase B - Preparation | 2020-05-24 | 3 | 8100 | 1
102 | Phase C - Development | 2020-06-02 | 199 | 10500 | 15
102 | Phase D - Testing | 2020-11-01 | 172 | 2800 | 28
102 | Phase E - Deployment | 2020-12-02 | 71 | 62000 | 12
102 | Phase F - Post-deployment | 2021-04-30 | 12 | 1400 | 5
103 | Phase A - Initiation | 2020-05-09 | 9 | 400 | 2
103 | Phase B - Preparation | 2020-09-02 | 5 | 8100 | 6
103 | Phase C - Development | 2020-10-13 | 1 | 10500 | 1
103 | Phase D - Testing | 2021-01-06 | 102 | 2800 | 13
103 | Phase E - Deployment | 2021-02-06 | 175 | 68000 | 20
103 | Phase F - Post-deployment | 2021-04-21 | 167 | 1400 | 24
104 | Phase 1 - Planning | 2018-05-12 | 186 | 50000 | 21
104 | Phase 2 - Initiation | 2018-06-07 | 185 | 100000 | 27
104 | Phase 3 - Implementation | 2018-06-23 | 72 | 150000 | 17
104 | Phase 4 - Manufacturing | 2018-12-08 | 191 | 450000 | 4

## Project type
In this tab are the project type for each Sanitoral project
Project ID | Project Type
1 | Marketing - Launch of new product
2 | Marketing - Launch of new product
3 | Marketing - Launch of new product
4 | Marketing - Launch of new product
5 | Marketing - Launch of new product
6 | Marketing - Launch of new product
7 | Marketing - Launch of new product
8 | Marketing - Launch of new product
9 | Marketing - Launch of new product
10 | Marketing - Launch of new product
11 | Marketing - Launch of new product
12 | Marketing - Launch of new product
13 | Marketing - Launch of new product
14 | Marketing - Launch of new product
15 | Marketing - Launch of new product
16 | Marketing - Launch of new product
17 | Marketing - Launch of new product
18 | Marketing - Launch of new product
19 | Marketing - Launch of new product
20 | Marketing - Launch of new product
21 | Marketing - Launch of new product
22 | Marketing - Launch of new product
23 | Marketing - Launch of new product
24 | Marketing - Launch of new product
25 | Marketing - Launch of new product
26 | Marketing - Launch of new product
27 | Marketing - Launch of new product
28 | Marketing - Launch of new product
29 | Marketing - Launch of new product
30 | Marketing - Launch of new product
31 | Marketing - Launch of new product
32 | Marketing - Launch of new product
33 | Marketing - Launch of new product
34 | Marketing - Launch of new product
35 | Marketing - Launch of new product
36 | Marketing - Launch of new product
37 | Marketing - Launch of new product
38 | Marketing - Launch of new product
39 | Marketing - Launch of new product
40 | Marketing - Launch of new product
41 | Marketing - Launch of new product
42 | Marketing - Launch of new product
43 | Marketing - Launch of new product
44 | Marketing - Launch of new product
45 | Marketing - Launch of new product
46 | Marketing - Launch of new product
47 | Marketing - Launch of new product
48 | Marketing - Launch of new product
49 | Marketing - Launch of new product
50 | Marketing - Launch of new product
51 | Marketing - Launch of new product
52 | IT - CRM Implementation
53 | IT - CRM Implementation
54 | IT - CRM Implementation
55 | IT - CRM Implementation
56 | IT - CRM Implementation
57 | IT - CRM Implementation
58 | IT - CRM Implementation
59 | IT - CRM Implementation
60 | IT - CRM Implementation
61 | IT - CRM Implementation
62 | IT - CRM Implementation
63 | IT - CRM Implementation
64 | IT - CRM Implementation
65 | IT - CRM Implementation
66 | IT - CRM Implementation
67 | IT - CRM Implementation
68 | IT - CRM Implementation
69 | IT - CRM Implementation
70 | IT - CRM Implementation
71 | IT - CRM Implementation
72 | IT - CRM Implementation
73 | IT - CRM Implementation
74 | IT - CRM Implementation
75 | IT - CRM Implementation
76 | IT - CRM Implementation
77 | IT - CRM Implementation
78 | IT - CRM Implementation
79 | IT - CRM Implementation
80 | IT - CRM Implementation
81 | IT - CRM Implementation
82 | IT - CRM Implementation
83 | IT - CRM Implementation
84 | IT - CRM Implementation
85 | IT - CRM Implementation
86 | IT - CRM Implementation
87 | IT - CRM Implementation
88 | IT - CRM Implementation
89 | IT - CRM Implementation
90 | IT - CRM Implementation
91 | IT - CRM Implementation
92 | IT - CRM Implementation
93 | IT - CRM Implementation
94 | IT - CRM Implementation
95 | IT - CRM Implementation
96 | IT - CRM Implementation
97 | IT - CRM Implementation
98 | IT - CRM Implementation
99 | IT - CRM Implementation
100 | IT - CRM Implementation
101 | IT - CRM Implementation
102 | IT - CRM Implementation
103 | IT - CRM Implementation
104 | Marketing - Launch of new product

## Actual_Costs
In this tab, are the actual projects costs for each projects
Proj_ID | Phase | Actual_Cost
1 | Phase 1 - Planning | 61500
2 | Phase 1 - Planning | 90200
3 | Phase 1 - Planning | 66900
4 | Phase 1 - Planning | 66200
5 | Phase 1 - Planning | 53600
6 | Phase 1 - Planning | 61500
7 | Phase 1 - Planning | 103700
8 | Phase 1 - Planning | 106100
9 | Phase 1 - Planning | 123100
10 | Phase 1 - Planning | 31300
11 | Phase 1 - Planning | 117400
12 | Phase 1 - Planning | 46600
13 | Phase 1 - Planning | 47500
14 | Phase 1 - Planning | 63700
15 | Phase 1 - Planning | 33900
16 | Phase 1 - Planning | 43400
17 | Phase 1 - Planning | 105000
18 | Phase 1 - Planning | 32200
19 | Phase 1 - Planning | 101300
20 | Phase 1 - Planning | 65300
21 | Phase 1 - Planning | 56000
22 | Phase 1 - Planning | 54400
23 | Phase 1 - Planning | 133500
24 | Phase 1 - Planning | 53000
25 | Phase 1 - Planning | 37600
26 | Phase 1 - Planning | 108200
27 | Phase 1 - Planning | 55500
28 | Phase 1 - Planning | 101900
29 | Phase 1 - Planning | 57900
30 | Phase 1 - Planning | 102800
31 | Phase 1 - Planning | 111400
32 | Phase 1 - Planning | 65100
33 | Phase 1 - Planning | 47000
34 | Phase 1 - Planning | 115300
35 | Phase 1 - Planning | 100400
36 | Phase 1 - Planning | 51700
37 | Phase 1 - Planning | 64200
38 | Phase 1 - Planning | 48800
39 | Phase 1 - Planning | 126400
40 | Phase 1 - Planning | 37700
41 | Phase 1 - Planning | 127500
42 | Phase 1 - Planning | 60900
43 | Phase 1 - Planning | 120400
44 | Phase 1 - Planning | 51600
45 | Phase 1 - Planning | 43300
46 | Phase 1 - Planning | 69700
47 | Phase 1 - Planning | 32700
48 | Phase 1 - Planning | 106000
49 | Phase 1 - Planning | 57200
50 | Phase 1 - Planning | 65700
51 | Phase 1 - Planning | 115800
104 | Phase 1 - Planning | 50400
1 | Phase 2 - Initiation | 124000
2 | Phase 2 - Initiation | 175200
3 | Phase 2 - Initiation | 128100
4 | Phase 2 - Initiation | 134900
5 | Phase 2 - Initiation | 97000
6 | Phase 2 - Initiation | 123700
7 | Phase 2 - Initiation | 209300
8 | Phase 2 - Initiation | 220400
9 | Phase 2 - Initiation | 234000
10 | Phase 2 - Initiation | 59600
11 | Phase 2 - Initiation | 223100
12 | Phase 2 - Initiation | 92300
13 | Phase 2 - Initiation | 87900
14 | Phase 2 - Initiation | 124600
15 | Phase 2 - Initiation | 66100
16 | Phase 2 - Initiation | 94900
17 | Phase 2 - Initiation | 186300
18 | Phase 2 - Initiation | 63600
19 | Phase 2 - Initiation | 210500
20 | Phase 2 - Initiation | 123200
21 | Phase 2 - Initiation | 108300
22 | Phase 2 - Initiation | 111600
23 | Phase 2 - Initiation | 266200
24 | Phase 2 - Initiation | 108300
25 | Phase 2 - Initiation | 76800
26 | Phase 2 - Initiation | 236900
27 | Phase 2 - Initiation | 101800
28 | Phase 2 - Initiation | 198300
29 | Phase 2 - Initiation | 117100
30 | Phase 2 - Initiation | 225900
31 | Phase 2 - Initiation | 230500
32 | Phase 2 - Initiation | 137400
33 | Phase 2 - Initiation | 88600
34 | Phase 2 - Initiation | 232600
35 | Phase 2 - Initiation | 206200
36 | Phase 2 - Initiation | 106700
37 | Phase 2 - Initiation | 121000
38 | Phase 2 - Initiation | 90400
39 | Phase 2 - Initiation | 237600
40 | Phase 2 - Initiation | 73700
41 | Phase 2 - Initiation | 240700
42 | Phase 2 - Initiation | 138100
43 | Phase 2 - Initiation | 269200
44 | Phase 2 - Initiation | 105100
45 | Phase 2 - Initiation | 91900
46 | Phase 2 - Initiation | 132700
47 | Phase 2 - Initiation | 63700
48 | Phase 2 - Initiation | 216400
49 | Phase 2 - Initiation | 123800
50 | Phase 2 - Initiation | 137700
51 | Phase 2 - Initiation | 238300
104 | Phase 2 - Initiation | 104300
1 | Phase 3 - Implementation | 201900
2 | Phase 3 - Implementation | 278100
3 | Phase 3 - Implementation | 197600
4 | Phase 3 - Implementation | 182300
5 | Phase 3 - Implementation | 151600
6 | Phase 3 - Implementation | 199200
7 | Phase 3 - Implementation | 287500
8 | Phase 3 - Implementation | 313700
9 | Phase 3 - Implementation | 371100
10 | Phase 3 - Implementation | 101800
11 | Phase 3 - Implementation | 353200
12 | Phase 3 - Implementation | 134400
13 | Phase 3 - Implementation | 131800
14 | Phase 3 - Implementation | 178100
15 | Phase 3 - Implementation | 108500
16 | Phase 3 - Implementation | 136600
17 | Phase 3 - Implementation | 322700
18 | Phase 3 - Implementation | 92000
19 | Phase 3 - Implementation | 313300
20 | Phase 3 - Implementation | 175900
21 | Phase 3 - Implementation | 165500
22 | Phase 3 - Implementation | 176000
23 | Phase 3 - Implementation | 348100
24 | Phase 3 - Implementation | 158300
25 | Phase 3 - Implementation | 122500
26 | Phase 3 - Implementation | 328900
27 | Phase 3 - Implementation | 148700
28 | Phase 3 - Implementation | 327500
29 | Phase 3 - Implementation | 178900
30 | Phase 3 - Implementation | 328900
31 | Phase 3 - Implementation | 341200
32 | Phase 3 - Implementation | 184300
33 | Phase 3 - Implementation | 140700
34 | Phase 3 - Implementation | 325100
35 | Phase 3 - Implementation | 331100
36 | Phase 3 - Implementation | 167300
37 | Phase 3 - Implementation | 182200
38 | Phase 3 - Implementation | 150000
39 | Phase 3 - Implementation | 385300
40 | Phase 3 - Implementation | 107500
41 | Phase 3 - Implementation | 376900
42 | Phase 3 - Implementation | 202700
43 | Phase 3 - Implementation | 401500
44 | Phase 3 - Implementation | 157700
45 | Phase 3 - Implementation | 131900
46 | Phase 3 - Implementation | 210600
47 | Phase 3 - Implementation | 86100
48 | Phase 3 - Implementation | 361600
49 | Phase 3 - Implementation | 171400
50 | Phase 3 - Implementation | 183300
51 | Phase 3 - Implementation | 354100
104 | Phase 3 - Implementation | 150000
1 | Phase 4 - Manufacturing | 558200
2 | Phase 4 - Manufacturing | 802500
3 | Phase 4 - Manufacturing | 562500
4 | Phase 4 - Manufacturing | 598300
5 | Phase 4 - Manufacturing | 483400
6 | Phase 4 - Manufacturing | 527400
7 | Phase 4 - Manufacturing | 886600
8 | Phase 4 - Manufacturing | 924100
9 | Phase 4 - Manufacturing | 1021100
10 | Phase 4 - Manufacturing | 288800
11 | Phase 4 - Manufacturing | 1017800
12 | Phase 4 - Manufacturing | 450200
13 | Phase 4 - Manufacturing | 418200
14 | Phase 4 - Manufacturing | 588500
15 | Phase 4 - Manufacturing | 302200
16 | Phase 4 - Manufacturing | 404600
17 | Phase 4 - Manufacturing | 925900
18 | Phase 4 - Manufacturing | 275400
19 | Phase 4 - Manufacturing | 908700
20 | Phase 4 - Manufacturing | 573200
21 | Phase 4 - Manufacturing | 468300
22 | Phase 4 - Manufacturing | 484700
23 | Phase 4 - Manufacturing | 1188200
24 | Phase 4 - Manufacturing | 445600
25 | Phase 4 - Manufacturing | 340600
26 | Phase 4 - Manufacturing | 986000
27 | Phase 4 - Manufacturing | 462700
28 | Phase 4 - Manufacturing | 920600
29 | Phase 4 - Manufacturing | 567300
30 | Phase 4 - Manufacturing | 923600
31 | Phase 4 - Manufacturing | 950000
32 | Phase 4 - Manufacturing | 621700
33 | Phase 4 - Manufacturing | 426600
34 | Phase 4 - Manufacturing | 974400
35 | Phase 4 - Manufacturing | 993600
36 | Phase 4 - Manufacturing | 514800
37 | Phase 4 - Manufacturing | 592300
38 | Phase 4 - Manufacturing | 393700
39 | Phase 4 - Manufacturing | 1072900
40 | Phase 4 - Manufacturing | 333200
41 | Phase 4 - Manufacturing | 1058500
42 | Phase 4 - Manufacturing | 617300
43 | Phase 4 - Manufacturing | 1103300
44 | Phase 4 - Manufacturing | 467500
45 | Phase 4 - Manufacturing | 371400
46 | Phase 4 - Manufacturing | 624200
47 | Phase 4 - Manufacturing | 285500
48 | Phase 4 - Manufacturing | 977900
49 | Phase 4 - Manufacturing | 516500
50 | Phase 4 - Manufacturing | 580500
51 | Phase 4 - Manufacturing | 999800
104 | Phase 4 - Manufacturing | 433200
52 | Phase A - Initiation | 900
53 | Phase A - Initiation | 700
54 | Phase A - Initiation | 800
55 | Phase A - Initiation | 800
56 | Phase A - Initiation | 700
57 | Phase A - Initiation | 700
58 | Phase A - Initiation | 900
59 | Phase A - Initiation | 400
60 | Phase A - Initiation | 400
61 | Phase A - Initiation | 800
62 | Phase A - Initiation | 1000
63 | Phase A - Initiation | 800
64 | Phase A - Initiation | 400
65 | Phase A - Initiation | 400
66 | Phase A - Initiation | 900
67 | Phase A - Initiation | 400
68 | Phase A - Initiation | 300
69 | Phase A - Initiation | 800
70 | Phase A - Initiation | 400
71 | Phase A - Initiation | 300
72 | Phase A - Initiation | 500
73 | Phase A - Initiation | 400
74 | Phase A - Initiation | 400
75 | Phase A - Initiation | 700
76 | Phase A - Initiation | 500
77 | Phase A - Initiation | 400
78 | Phase A - Initiation | 400
79 | Phase A - Initiation | 800
80 | Phase A - Initiation | 800
81 | Phase A - Initiation | 900
82 | Phase A - Initiation | 700
83 | Phase A - Initiation | 300
84 | Phase A - Initiation | 200
85 | Phase A - Initiation | 400
86 | Phase A - Initiation | 300
87 | Phase A - Initiation | 200
88 | Phase A - Initiation | 300
89 | Phase A - Initiation | 300
90 | Phase A - Initiation | 300
91 | Phase A - Initiation | 200
92 | Phase A - Initiation | 400
93 | Phase A - Initiation | 400
94 | Phase A - Initiation | 700
95 | Phase A - Initiation | 400
96 | Phase A - Initiation | 300
97 | Phase A - Initiation | 500
98 | Phase A - Initiation | 400
99 | Phase A - Initiation | 400
100 | Phase A - Initiation | 400
101 | Phase A - Initiation | 700
102 | Phase A - Initiation | 500
103 | Phase A - Initiation | 400
52 | Phase B - Preparation | 21500
53 | Phase B - Preparation | 16400
54 | Phase B - Preparation | 19300
55 | Phase B - Preparation | 20000
56 | Phase B - Preparation | 15300
57 | Phase B - Preparation | 15200
58 | Phase B - Preparation | 20100
59 | Phase B - Preparation | 13500
60 | Phase B - Preparation | 13300
61 | Phase B - Preparation | 18200
62 | Phase B - Preparation | 21500
63 | Phase B - Preparation | 18600
64 | Phase B - Preparation | 11800
65 | Phase B - Preparation | 9700
66 | Phase B - Preparation | 22000
67 | Phase B - Preparation | 8900
68 | Phase B - Preparation | 8100
69 | Phase B - Preparation | 19300
70 | Phase B - Preparation | 9600
71 | Phase B - Preparation | 10400
72 | Phase B - Preparation | 10100
73 | Phase B - Preparation | 9800
74 | Phase B - Preparation | 8800
75 | Phase B - Preparation | 16200
76 | Phase B - Preparation | 10700
77 | Phase B - Preparation | 9100
78 | Phase B - Preparation | 9800
79 | Phase B - Preparation | 18900
80 | Phase B - Preparation | 19800
81 | Phase B - Preparation | 20000
82 | Phase B - Preparation | 16600
83 | Phase B - Preparation | 5400
84 | Phase B - Preparation | 5100
85 | Phase B - Preparation | 9500
86 | Phase B - Preparation | 6600
87 | Phase B - Preparation | 5200
88 | Phase B - Preparation | 7200
89 | Phase B - Preparation | 6400
90 | Phase B - Preparation | 6500
91 | Phase B - Preparation | 5000
92 | Phase B - Preparation | 8500
93 | Phase B - Preparation | 10400
94 | Phase B - Preparation | 18500
95 | Phase B - Preparation | 12700
96 | Phase B - Preparation | 12700
97 | Phase B - Preparation | 9900
98 | Phase B - Preparation | 11300
99 | Phase B - Preparation | 16200
100 | Phase B - Preparation | 12200
101 | Phase B - Preparation | 17700
102 | Phase B - Preparation | 10500
103 | Phase B - Preparation | 15200
52 | Phase C - Development | 25500
53 | Phase C - Development | 24000
54 | Phase C - Development | 25900
55 | Phase C - Development | 26900
56 | Phase C - Development | 19200
57 | Phase C - Development | 21700
58 | Phase C - Development | 24600
59 | Phase C - Development | 9800
60 | Phase C - Development | 12400
61 | Phase C - Development | 23600
62 | Phase C - Development | 26800
63 | Phase C - Development | 23800
64 | Phase C - Development | 13700
65 | Phase C - Development | 12500
66 | Phase C - Development | 26200
67 | Phase C - Development | 11400
68 | Phase C - Development | 10300
69 | Phase C - Development | 23200
70 | Phase C - Development | 13800
71 | Phase C - Development | 10500
72 | Phase C - Development | 13400
73 | Phase C - Development | 13300
74 | Phase C - Development | 10400
75 | Phase C - Development | 21500
76 | Phase C - Development | 13900
77 | Phase C - Development | 10900
78 | Phase C - Development | 12300
79 | Phase C - Development | 25300
80 | Phase C - Development | 23600
81 | Phase C - Development | 25600
82 | Phase C - Development | 22800
83 | Phase C - Development | 7600
84 | Phase C - Development | 6800
85 | Phase C - Development | 13200
86 | Phase C - Development | 7800
87 | Phase C - Development | 6700
88 | Phase C - Development | 8500
89 | Phase C - Development | 7600
90 | Phase C - Development | 7600
91 | Phase C - Development | 7100
92 | Phase C - Development | 12000
93 | Phase C - Development | 13300
94 | Phase C - Development | 22700
95 | Phase C - Development | 11500
96 | Phase C - Development | 10600
97 | Phase C - Development | 14500
98 | Phase C - Development | 14400
99 | Phase C - Development | 14100
100 | Phase C - Development | 9300
101 | Phase C - Development | 20700
102 | Phase C - Development | 13500
103 | Phase C - Development | 13400
52 | Phase D - Testing | 19000
53 | Phase D - Testing | 26600
54 | Phase D - Testing | 16700
55 | Phase D - Testing | 18200
56 | Phase D - Testing | 18500
57 | Phase D - Testing | 16100
58 | Phase D - Testing | 17900
59 | Phase D - Testing | 14300
60 | Phase D - Testing | 18800
61 | Phase D - Testing | 20800
62 | Phase D - Testing | 18400
63 | Phase D - Testing | 25600
64 | Phase D - Testing | 19200
65 | Phase D - Testing | 16900
66 | Phase D - Testing | 29800
67 | Phase D - Testing | 18000
68 | Phase D - Testing | 19300
69 | Phase D - Testing | 22600
70 | Phase D - Testing | 15900
71 | Phase D - Testing | 14600
72 | Phase D - Testing | 15000
73 | Phase D - Testing | 23200
74 | Phase D - Testing | 13300
75 | Phase D - Testing | 16800
76 | Phase D - Testing | 14500
77 | Phase D - Testing | 17700
78 | Phase D - Testing | 22400
79 | Phase D - Testing | 24000
80 | Phase D - Testing | 25800
81 | Phase D - Testing | 19200
82 | Phase D - Testing | 24100
83 | Phase D - Testing | 19100
84 | Phase D - Testing | 14100
85 | Phase D - Testing | 22400
86 | Phase D - Testing | 20900
87 | Phase D - Testing | 20800
88 | Phase D - Testing | 17800
89 | Phase D - Testing | 16100
90 | Phase D - Testing | 14100
91 | Phase D - Testing | 20900
92 | Phase D - Testing | 15400
93 | Phase D - Testing | 20700
94 | Phase D - Testing | 18300
95 | Phase D - Testing | 19500
96 | Phase D - Testing | 15700
97 | Phase D - Testing | 14700
98 | Phase D - Testing | 19500
99 | Phase D - Testing | 16200
100 | Phase D - Testing | 20900
101 | Phase D - Testing | 19900
102 | Phase D - Testing | 21600
103 | Phase D - Testing | 20100
52 | Phase E - Deployment | 36600
53 | Phase E - Deployment | 26500
54 | Phase E - Deployment | 40000
55 | Phase E - Deployment | 24800
56 | Phase E - Deployment | 25300
57 | Phase E - Deployment | 51300
58 | Phase E - Deployment | 53700
59 | Phase E - Deployment | 47800
60 | Phase E - Deployment | 23700
61 | Phase E - Deployment | 44900
62 | Phase E - Deployment | 44800
63 | Phase E - Deployment | 52500
64 | Phase E - Deployment | 58000
65 | Phase E - Deployment | 34200
66 | Phase E - Deployment | 28800
67 | Phase E - Deployment | 53300
68 | Phase E - Deployment | 22700
69 | Phase E - Deployment | 52900
70 | Phase E - Deployment | 37000
71 | Phase E - Deployment | 44500
72 | Phase E - Deployment | 28400
73 | Phase E - Deployment | 50600
74 | Phase E - Deployment | 42500
75 | Phase E - Deployment | 53100
76 | Phase E - Deployment | 47800
77 | Phase E - Deployment | 25000
78 | Phase E - Deployment | 23400
79 | Phase E - Deployment | 43300
80 | Phase E - Deployment | 26000
81 | Phase E - Deployment | 52600
82 | Phase E - Deployment | 43400
83 | Phase E - Deployment | 20600
84 | Phase E - Deployment | 57400
85 | Phase E - Deployment | 43000
86 | Phase E - Deployment | 45500
87 | Phase E - Deployment | 32800
88 | Phase E - Deployment | 58400
89 | Phase E - Deployment | 33000
90 | Phase E - Deployment | 34400
91 | Phase E - Deployment | 37000
92 | Phase E - Deployment | 21900
93 | Phase E - Deployment | 38100
94 | Phase E - Deployment | 47500
95 | Phase E - Deployment | 30800
96 | Phase E - Deployment | 20400
97 | Phase E - Deployment | 41200
98 | Phase E - Deployment | 43600
99 | Phase E - Deployment | 31100
100 | Phase E - Deployment | 22700
101 | Phase E - Deployment | 38800
102 | Phase E - Deployment | 33500
103 | Phase E - Deployment | 40900
52 | Phase F - Post-deployment | 3300
53 | Phase F - Post-deployment | 3000
54 | Phase F - Post-deployment | 3100
55 | Phase F - Post-deployment | 3400
56 | Phase F - Post-deployment | 2900
57 | Phase F - Post-deployment | 2800
58 | Phase F - Post-deployment | 3200
59 | Phase F - Post-deployment | 1300
60 | Phase F - Post-deployment | 1600
61 | Phase F - Post-deployment | 2900
62 | Phase F - Post-deployment | 3600
63 | Phase F - Post-deployment | 3300
64 | Phase F - Post-deployment | 1800
65 | Phase F - Post-deployment | 1600
66 | Phase F - Post-deployment | 3900
67 | Phase F - Post-deployment | 1600
68 | Phase F - Post-deployment | 1400
69 | Phase F - Post-deployment | 3400
70 | Phase F - Post-deployment | 1600
71 | Phase F - Post-deployment | 1400
72 | Phase F - Post-deployment | 1900
73 | Phase F - Post-deployment | 1700
74 | Phase F - Post-deployment | 1400
75 | Phase F - Post-deployment | 2800
76 | Phase F - Post-deployment | 1900
77 | Phase F - Post-deployment | 1600
78 | Phase F - Post-deployment | 1800
79 | Phase F - Post-deployment | 3100
80 | Phase F - Post-deployment | 3300
81 | Phase F - Post-deployment | 3500
82 | Phase F - Post-deployment | 2800
83 | Phase F - Post-deployment | 1000
84 | Phase F - Post-deployment | 900
85 | Phase F - Post-deployment | 1700
86 | Phase F - Post-deployment | 1100
87 | Phase F - Post-deployment | 900
88 | Phase F - Post-deployment | 1200
89 | Phase F - Post-deployment | 1000
90 | Phase F - Post-deployment | 1000
91 | Phase F - Post-deployment | 900
92 | Phase F - Post-deployment | 1400
93 | Phase F - Post-deployment | 1800
94 | Phase F - Post-deployment | 3200
95 | Phase F - Post-deployment | 1600
96 | Phase F - Post-deployment | 1400
97 | Phase F - Post-deployment | 1800
98 | Phase F - Post-deployment | 1900
99 | Phase F - Post-deployment | 1700
100 | Phase F - Post-deployment | 1300
101 | Phase F - Post-deployment | 2900
102 | Phase F - Post-deployment | 1800
103 | Phase F - Post-deployment | 1900

## Actual_Duration
In this tabn are the duration observed for each project for each of their phases
Project | Phase | Actual_Duration
1 | Phase 1 - Planning | 196
1 | Phase 2 - Initiation | 7
1 | Phase 3 - Implementation | 176
1 | Phase 4 - Manufacturing | 64
2 | Phase 1 - Planning | 16
2 | Phase 2 - Initiation | 66
2 | Phase 3 - Implementation | 73
2 | Phase 4 - Manufacturing | 148
3 | Phase 1 - Planning | 124
3 | Phase 2 - Initiation | 34
3 | Phase 3 - Implementation | 178
3 | Phase 4 - Manufacturing | 127
4 | Phase 1 - Planning | 17
4 | Phase 2 - Initiation | 25
4 | Phase 3 - Implementation | 147
4 | Phase 4 - Manufacturing | 105
5 | Phase 1 - Planning | 25
5 | Phase 2 - Initiation | 157
5 | Phase 3 - Implementation | 62
5 | Phase 4 - Manufacturing | 52
6 | Phase 1 - Planning | 57
6 | Phase 2 - Initiation | 183
6 | Phase 3 - Implementation | 89
6 | Phase 4 - Manufacturing | 58
7 | Phase 1 - Planning | 151
7 | Phase 2 - Initiation | 26
7 | Phase 3 - Implementation | 143
7 | Phase 4 - Manufacturing | 120
8 | Phase 1 - Planning | 66
8 | Phase 2 - Initiation | 68
8 | Phase 3 - Implementation | 6
8 | Phase 4 - Manufacturing | 135
9 | Phase 1 - Planning | 135
9 | Phase 2 - Initiation | 52
9 | Phase 3 - Implementation | 4
9 | Phase 4 - Manufacturing | 73
10 | Phase 1 - Planning | 132
10 | Phase 2 - Initiation | 16
10 | Phase 3 - Implementation | 31
10 | Phase 4 - Manufacturing | 15
11 | Phase 1 - Planning | 78
11 | Phase 2 - Initiation | 9
11 | Phase 3 - Implementation | 168
11 | Phase 4 - Manufacturing | 67
12 | Phase 1 - Planning | 8
12 | Phase 2 - Initiation | 153
12 | Phase 3 - Implementation | 144
12 | Phase 4 - Manufacturing | 104
13 | Phase 1 - Planning | 106
13 | Phase 2 - Initiation | 97
13 | Phase 3 - Implementation | 139
13 | Phase 4 - Manufacturing | 153
14 | Phase 1 - Planning | 150
14 | Phase 2 - Initiation | 122
14 | Phase 3 - Implementation | 14
14 | Phase 4 - Manufacturing | 55
15 | Phase 1 - Planning | 164
15 | Phase 2 - Initiation | 171
15 | Phase 3 - Implementation | 41
15 | Phase 4 - Manufacturing | 71
16 | Phase 1 - Planning | 25
16 | Phase 2 - Initiation | 115
16 | Phase 3 - Implementation | 100
16 | Phase 4 - Manufacturing | 32
17 | Phase 1 - Planning | 97
17 | Phase 2 - Initiation | 67
17 | Phase 3 - Implementation | 147
17 | Phase 4 - Manufacturing | 61
18 | Phase 1 - Planning | 64
18 | Phase 2 - Initiation | 65
18 | Phase 3 - Implementation | 41
18 | Phase 4 - Manufacturing | 100
19 | Phase 1 - Planning | 200
19 | Phase 2 - Initiation | 155
19 | Phase 3 - Implementation | 110
19 | Phase 4 - Manufacturing | 144
20 | Phase 1 - Planning | 125
20 | Phase 2 - Initiation | 84
20 | Phase 3 - Implementation | 99
20 | Phase 4 - Manufacturing | 121
21 | Phase 1 - Planning | 54
21 | Phase 2 - Initiation | 70
21 | Phase 3 - Implementation | 106
21 | Phase 4 - Manufacturing | 145
22 | Phase 1 - Planning | 139
22 | Phase 2 - Initiation | 125
22 | Phase 3 - Implementation | 154
22 | Phase 4 - Manufacturing | 123
23 | Phase 1 - Planning | 57
23 | Phase 2 - Initiation | 7
23 | Phase 3 - Implementation | 135
23 | Phase 4 - Manufacturing | 14
24 | Phase 1 - Planning | 87
24 | Phase 2 - Initiation | 132
24 | Phase 3 - Implementation | 54
24 | Phase 4 - Manufacturing | 165
25 | Phase 1 - Planning | 30
25 | Phase 2 - Initiation | 199
25 | Phase 3 - Implementation | 63
25 | Phase 4 - Manufacturing | 73
26 | Phase 1 - Planning | 95
26 | Phase 2 - Initiation | 45
26 | Phase 3 - Implementation | 112
26 | Phase 4 - Manufacturing | 1
27 | Phase 1 - Planning | 99
27 | Phase 2 - Initiation | 151
27 | Phase 3 - Implementation | 28
27 | Phase 4 - Manufacturing | 168
28 | Phase 1 - Planning | 13
28 | Phase 2 - Initiation | 51
28 | Phase 3 - Implementation | 218
28 | Phase 4 - Manufacturing | 32
29 | Phase 1 - Planning | 14
29 | Phase 2 - Initiation | 43
29 | Phase 3 - Implementation | 116
29 | Phase 4 - Manufacturing | 3
30 | Phase 1 - Planning | 112
30 | Phase 2 - Initiation | 126
30 | Phase 3 - Implementation | 30
30 | Phase 4 - Manufacturing | 141
31 | Phase 1 - Planning | 36
31 | Phase 2 - Initiation | 50
31 | Phase 3 - Implementation | 54
31 | Phase 4 - Manufacturing | 49
32 | Phase 1 - Planning | 56
32 | Phase 2 - Initiation | 25
32 | Phase 3 - Implementation | 108
32 | Phase 4 - Manufacturing | 21
33 | Phase 1 - Planning | 53
33 | Phase 2 - Initiation | 100
33 | Phase 3 - Implementation | 62
33 | Phase 4 - Manufacturing | 82
34 | Phase 1 - Planning | 38
34 | Phase 2 - Initiation | 128
34 | Phase 3 - Implementation | 132
34 | Phase 4 - Manufacturing | 99
35 | Phase 1 - Planning | 30
35 | Phase 2 - Initiation | 96
35 | Phase 3 - Implementation | 77
35 | Phase 4 - Manufacturing | 122
36 | Phase 1 - Planning | 44
36 | Phase 2 - Initiation | 57
36 | Phase 3 - Implementation | 144
36 | Phase 4 - Manufacturing | 74
37 | Phase 1 - Planning | 12
37 | Phase 2 - Initiation | 75
37 | Phase 3 - Implementation | 92
37 | Phase 4 - Manufacturing | 78
38 | Phase 1 - Planning | 56
38 | Phase 2 - Initiation | 84
38 | Phase 3 - Implementation | 135
38 | Phase 4 - Manufacturing | 74
39 | Phase 1 - Planning | 16
39 | Phase 2 - Initiation | 148
39 | Phase 3 - Implementation | 12
39 | Phase 4 - Manufacturing | 172
40 | Phase 1 - Planning | 198
40 | Phase 2 - Initiation | 121
40 | Phase 3 - Implementation | 90
40 | Phase 4 - Manufacturing | 54
41 | Phase 1 - Planning | 84
41 | Phase 2 - Initiation | 100
41 | Phase 3 - Implementation | 40
41 | Phase 4 - Manufacturing | 48
42 | Phase 1 - Planning | 93
42 | Phase 2 - Initiation | 86
42 | Phase 3 - Implementation | 63
42 | Phase 4 - Manufacturing | 18
43 | Phase 1 - Planning | 9
43 | Phase 2 - Initiation | 92
43 | Phase 3 - Implementation | 129
43 | Phase 4 - Manufacturing | 50
44 | Phase 1 - Planning | 56
44 | Phase 2 - Initiation | 102
44 | Phase 3 - Implementation | 166
44 | Phase 4 - Manufacturing | 116
45 | Phase 1 - Planning | 154
45 | Phase 2 - Initiation | 98
45 | Phase 3 - Implementation | 51
45 | Phase 4 - Manufacturing | 56
46 | Phase 1 - Planning | 12
46 | Phase 2 - Initiation | 17
46 | Phase 3 - Implementation | 106
46 | Phase 4 - Manufacturing | 90
47 | Phase 1 - Planning | 40
47 | Phase 2 - Initiation | 180
47 | Phase 3 - Implementation | 87
47 | Phase 4 - Manufacturing | 40
48 | Phase 1 - Planning | 27
48 | Phase 2 - Initiation | 90
48 | Phase 3 - Implementation | 119
48 | Phase 4 - Manufacturing | 133
49 | Phase 1 - Planning | 17
49 | Phase 2 - Initiation | 41
49 | Phase 3 - Implementation | 70
49 | Phase 4 - Manufacturing | 39
50 | Phase 1 - Planning | 62
50 | Phase 2 - Initiation | 56
50 | Phase 3 - Implementation | 40
50 | Phase 4 - Manufacturing | 118
51 | Phase 1 - Planning | 108
51 | Phase 2 - Initiation | 56
51 | Phase 3 - Implementation | 15
51 | Phase 4 - Manufacturing | 133
52 | Phase E - Deployment | 114
52 | Phase C - Development | 13
52 | Phase A - Initiation | 109
52 | Phase F - Post-deployment | 36
52 | Phase B - Preparation | 136
52 | Phase D - Testing | 58
53 | Phase E - Deployment | 128
53 | Phase C - Development | 70
53 | Phase A - Initiation | 44
53 | Phase F - Post-deployment | 106
53 | Phase B - Preparation | 78
53 | Phase D - Testing | 26
54 | Phase E - Deployment | 79
54 | Phase C - Development | 69
54 | Phase A - Initiation | 281
54 | Phase F - Post-deployment | 157
54 | Phase B - Preparation | 52
54 | Phase D - Testing | 153
55 | Phase E - Deployment | 89
55 | Phase C - Development | 31
55 | Phase A - Initiation | 44
55 | Phase F - Post-deployment | 12
55 | Phase B - Preparation | 139
55 | Phase D - Testing | 84
56 | Phase E - Deployment | 174
56 | Phase C - Development | 116
56 | Phase A - Initiation | 81
56 | Phase F - Post-deployment | 153
56 | Phase B - Preparation | 56
56 | Phase D - Testing | 9
57 | Phase E - Deployment | 56
57 | Phase C - Development | 133
57 | Phase A - Initiation | 165
57 | Phase F - Post-deployment | 88
57 | Phase B - Preparation | 125
57 | Phase D - Testing | 29
58 | Phase E - Deployment | 36
58 | Phase C - Development | 147
58 | Phase A - Initiation | 65
58 | Phase F - Post-deployment | 159
58 | Phase B - Preparation | 103
58 | Phase D - Testing | 77
59 | Phase E - Deployment | 124
59 | Phase C - Development | 38
59 | Phase A - Initiation | 28
59 | Phase F - Post-deployment | 15
59 | Phase B - Preparation | 32
59 | Phase D - Testing | 129
60 | Phase E - Deployment | 128
60 | Phase C - Development | 59
60 | Phase A - Initiation | 85
60 | Phase F - Post-deployment | 146
60 | Phase B - Preparation | 58
60 | Phase D - Testing | 175
61 | Phase E - Deployment | 67
61 | Phase C - Development | 144
61 | Phase A - Initiation | 130
61 | Phase F - Post-deployment | 99
61 | Phase B - Preparation | 49
61 | Phase D - Testing | 6
62 | Phase E - Deployment | 50
62 | Phase C - Development | 77
62 | Phase A - Initiation | 31
62 | Phase F - Post-deployment | 36
62 | Phase B - Preparation | 113
62 | Phase D - Testing | 57
63 | Phase E - Deployment | 138
63 | Phase C - Development | 143
63 | Phase A - Initiation | 28
63 | Phase F - Post-deployment | 121
63 | Phase B - Preparation | 12
63 | Phase D - Testing | 129
64 | Phase E - Deployment | 165
64 | Phase C - Development | 124
64 | Phase A - Initiation | 71
64 | Phase F - Post-deployment | 105
64 | Phase B - Preparation | 12
64 | Phase D - Testing | 119
65 | Phase E - Deployment | 53
65 | Phase C - Development | 8
65 | Phase A - Initiation | 107
65 | Phase F - Post-deployment | 161
65 | Phase B - Preparation | 123
65 | Phase D - Testing | 26
66 | Phase E - Deployment | 140
66 | Phase C - Development | 60
66 | Phase A - Initiation | 13
66 | Phase F - Post-deployment | 93
66 | Phase B - Preparation | 57
66 | Phase D - Testing | 148
67 | Phase E - Deployment | 131
67 | Phase C - Development | 63
67 | Phase A - Initiation | 7
67 | Phase F - Post-deployment | 89
67 | Phase B - Preparation | 35
67 | Phase D - Testing | 96
68 | Phase E - Deployment | 120
68 | Phase C - Development | 54
68 | Phase A - Initiation | 159
68 | Phase F - Post-deployment | 71
68 | Phase B - Preparation | 128
68 | Phase D - Testing | 66
69 | Phase E - Deployment | 17
69 | Phase C - Development | 58
69 | Phase A - Initiation | 81
69 | Phase F - Post-deployment | 110
69 | Phase B - Preparation | 134
69 | Phase D - Testing | 80
70 | Phase E - Deployment | 171
70 | Phase C - Development | 42
70 | Phase A - Initiation | 98
70 | Phase F - Post-deployment | 77
70 | Phase B - Preparation | 130
70 | Phase D - Testing | 5
71 | Phase E - Deployment | 124
71 | Phase C - Development | 4
71 | Phase A - Initiation | 79
71 | Phase F - Post-deployment | 112
71 | Phase B - Preparation | 173
71 | Phase D - Testing | 144
72 | Phase E - Deployment | 65
72 | Phase C - Development | 80
72 | Phase A - Initiation | 151
72 | Phase F - Post-deployment | 5
72 | Phase B - Preparation | 196
72 | Phase D - Testing | 64
73 | Phase E - Deployment | 19
73 | Phase C - Development | 11
73 | Phase A - Initiation | 86
73 | Phase F - Post-deployment | 102
73 | Phase B - Preparation | 73
73 | Phase D - Testing | 73
74 | Phase E - Deployment | 60
74 | Phase C - Development | 233
74 | Phase A - Initiation | 129
74 | Phase F - Post-deployment | 113
74 | Phase B - Preparation | 58
74 | Phase D - Testing | 117
75 | Phase E - Deployment | 77
75 | Phase C - Development | 124
75 | Phase A - Initiation | 8
75 | Phase F - Post-deployment | 97
75 | Phase B - Preparation | 56
75 | Phase D - Testing | 73
76 | Phase E - Deployment | 71
76 | Phase C - Development | 138
76 | Phase A - Initiation | 45
76 | Phase F - Post-deployment | 55
76 | Phase B - Preparation | 120
76 | Phase D - Testing | 25
77 | Phase E - Deployment | 102
77 | Phase C - Development | 132
77 | Phase A - Initiation | 11
77 | Phase F - Post-deployment | 159
77 | Phase B - Preparation | 129
77 | Phase D - Testing | 121
78 | Phase E - Deployment | 58
78 | Phase C - Development | 27
78 | Phase A - Initiation | 140
78 | Phase F - Post-deployment | 129
78 | Phase B - Preparation | 128
78 | Phase D - Testing | 39
79 | Phase E - Deployment | 67
79 | Phase C - Development | 72
79 | Phase A - Initiation | 109
79 | Phase F - Post-deployment | 108
79 | Phase B - Preparation | 156
79 | Phase D - Testing | 99
80 | Phase E - Deployment | 70
80 | Phase C - Development | 141
80 | Phase A - Initiation | 138
80 | Phase F - Post-deployment | 83
80 | Phase B - Preparation | 133
80 | Phase D - Testing | 131
81 | Phase E - Deployment | 125
81 | Phase C - Development | 5
81 | Phase A - Initiation | 138
81 | Phase F - Post-deployment | 121
81 | Phase B - Preparation | 50
81 | Phase D - Testing | 63
82 | Phase E - Deployment | 37
82 | Phase C - Development | 13
82 | Phase A - Initiation | 65
82 | Phase F - Post-deployment | 104
82 | Phase B - Preparation | 163
82 | Phase D - Testing | 102
83 | Phase E - Deployment | 76
83 | Phase C - Development | 140
83 | Phase A - Initiation | 43
83 | Phase F - Post-deployment | 110
83 | Phase B - Preparation | 100
83 | Phase D - Testing | 121
84 | Phase E - Deployment | 12
84 | Phase C - Development | 138
84 | Phase A - Initiation | 63
84 | Phase F - Post-deployment | 135
84 | Phase B - Preparation | 52
84 | Phase D - Testing | 53
85 | Phase E - Deployment | 135
85 | Phase C - Development | 11
85 | Phase A - Initiation | 82
85 | Phase F - Post-deployment | 172
85 | Phase B - Preparation | 96
85 | Phase D - Testing | 146
86 | Phase E - Deployment | 74
86 | Phase C - Development | 125
86 | Phase A - Initiation | 64
86 | Phase F - Post-deployment | 132
86 | Phase B - Preparation | 128
86 | Phase D - Testing | 53
87 | Phase E - Deployment | 178
87 | Phase C - Development | 116
87 | Phase A - Initiation | 83
87 | Phase F - Post-deployment | 152
87 | Phase B - Preparation | 19
87 | Phase D - Testing | 101
88 | Phase E - Deployment | 60
88 | Phase C - Development | 59
88 | Phase A - Initiation | 162
88 | Phase F - Post-deployment | 79
88 | Phase B - Preparation | 103
88 | Phase D - Testing | 146
89 | Phase E - Deployment | 95
89 | Phase C - Development | 123
89 | Phase A - Initiation | 17
89 | Phase F - Post-deployment | 97
89 | Phase B - Preparation | 170
89 | Phase D - Testing | 9
90 | Phase E - Deployment | 151
90 | Phase A - Initiation | 8
90 | Phase F - Post-deployment | 131
90 | Phase B - Preparation | 17
90 | Phase D - Testing | 55
91 | Phase E - Deployment | 118
91 | Phase C - Development | 92
91 | Phase A - Initiation | 46
91 | Phase F - Post-deployment | 92
91 | Phase B - Preparation | 124
91 | Phase D - Testing | 58
92 | Phase E - Deployment | 139
92 | Phase C - Development | 164
92 | Phase A - Initiation | 96
92 | Phase F - Post-deployment | 125
92 | Phase B - Preparation | 33
92 | Phase D - Testing | 113
93 | Phase E - Deployment | 132
93 | Phase C - Development | 60
93 | Phase A - Initiation | 43
93 | Phase F - Post-deployment | 37
93 | Phase B - Preparation | 104
93 | Phase D - Testing | 160
94 | Phase E - Deployment | 110
94 | Phase C - Development | 144
94 | Phase A - Initiation | 67
94 | Phase F - Post-deployment | 53
94 | Phase B - Preparation | 25
94 | Phase D - Testing | 130
95 | Phase E - Deployment | 101
95 | Phase C - Development | 145
95 | Phase A - Initiation | 45
95 | Phase F - Post-deployment | 102
95 | Phase B - Preparation | 27
95 | Phase D - Testing | 85
96 | Phase E - Deployment | 24
96 | Phase C - Development | 114
96 | Phase A - Initiation | 22
96 | Phase F - Post-deployment | 78
96 | Phase B - Preparation | 68
96 | Phase D - Testing | 100
97 | Phase E - Deployment | 142
97 | Phase C - Development | 76
97 | Phase A - Initiation | 60
97 | Phase F - Post-deployment | 23
97 | Phase B - Preparation | 206
97 | Phase D - Testing | 80
98 | Phase E - Deployment | 140
98 | Phase C - Development | 100
98 | Phase A - Initiation | 42
98 | Phase F - Post-deployment | 144
98 | Phase B - Preparation | 37
98 | Phase D - Testing | 40
99 | Phase E - Deployment | 147
99 | Phase C - Development | 54
99 | Phase A - Initiation | 83
99 | Phase F - Post-deployment | 55
99 | Phase B - Preparation | 16
99 | Phase D - Testing | 76
100 | Phase E - Deployment | 19
100 | Phase C - Development | 157
100 | Phase A - Initiation | 132
100 | Phase F - Post-deployment | 22
100 | Phase B - Preparation | 135
100 | Phase D - Testing | 150
101 | Phase E - Deployment | 6
101 | Phase C - Development | 175
101 | Phase A - Initiation | 69
101 | Phase F - Post-deployment | 89
101 | Phase B - Preparation | 71
101 | Phase D - Testing | 86
102 | Phase E - Deployment | 63
102 | Phase C - Development | 152
102 | Phase A - Initiation | 65
102 | Phase F - Post-deployment | 8
102 | Phase B - Preparation | 9
102 | Phase D - Testing | 141
103 | Phase E - Deployment | 75
103 | Phase C - Development | 8
103 | Phase A - Initiation | 11
103 | Phase F - Post-deployment | 171
103 | Phase B - Preparation | 4
103 | Phase D - Testing | 131
104 | Phase 1 - Planning | 163
104 | Phase 2 - Initiation | 179
104 | Phase 3 - Implementation | 168
104 | Phase 4 - Manufacturing | 140
90 | Phase C - Development | 75

## Actual_Delivrable
In this tab are the observed variance in terms of deliverables produced by the project per each phase
ID | Phase | Actual_Deliverables
1 | Phase 1 - Planning | 10
1 | Phase 2 - Initiation | 16
1 | Phase 3 - Implementation | 25
1 | Phase 4 - Manufacturing | 23
2 | Phase 1 - Planning | 6
2 | Phase 2 - Initiation | 23
2 | Phase 3 - Implementation | 15
2 | Phase 4 - Manufacturing | 19
3 | Phase 1 - Planning | 26
3 | Phase 2 - Initiation | 16
3 | Phase 3 - Implementation | 18
3 | Phase 4 - Manufacturing | 8
4 | Phase 1 - Planning | 20
4 | Phase 2 - Initiation | 19
4 | Phase 3 - Implementation | 29
4 | Phase 4 - Manufacturing | 23
5 | Phase 1 - Planning | 3
5 | Phase 2 - Initiation | 19
5 | Phase 3 - Implementation | 22
5 | Phase 4 - Manufacturing | 13
6 | Phase 1 - Planning | 18
6 | Phase 2 - Initiation | 6
6 | Phase 3 - Implementation | 12
6 | Phase 4 - Manufacturing | 4
7 | Phase 1 - Planning | 28
7 | Phase 2 - Initiation | 28
7 | Phase 3 - Implementation | 19
7 | Phase 4 - Manufacturing | 17
8 | Phase 1 - Planning | 25
8 | Phase 2 - Initiation | 4
8 | Phase 3 - Implementation | 10
8 | Phase 4 - Manufacturing | 17
9 | Phase 1 - Planning | 10
9 | Phase 2 - Initiation | 20
9 | Phase 3 - Implementation | 9
9 | Phase 4 - Manufacturing | 3
10 | Phase 1 - Planning | 25
10 | Phase 2 - Initiation | 28
10 | Phase 3 - Implementation | 22
10 | Phase 4 - Manufacturing | 4
11 | Phase 1 - Planning | 4
11 | Phase 2 - Initiation | 12
11 | Phase 3 - Implementation | 17
11 | Phase 4 - Manufacturing | 9
12 | Phase 1 - Planning | 20
12 | Phase 2 - Initiation | 3
12 | Phase 3 - Implementation | 3
12 | Phase 4 - Manufacturing | 19
13 | Phase 1 - Planning | 16
13 | Phase 2 - Initiation | 7
13 | Phase 3 - Implementation | 23
13 | Phase 4 - Manufacturing | 21
14 | Phase 1 - Planning | 9
14 | Phase 2 - Initiation | 29
14 | Phase 3 - Implementation | 1
14 | Phase 4 - Manufacturing | 20
15 | Phase 1 - Planning | 22
15 | Phase 2 - Initiation | 22
15 | Phase 3 - Implementation | 28
15 | Phase 4 - Manufacturing | 13
16 | Phase 1 - Planning | 6
16 | Phase 2 - Initiation | 6
16 | Phase 3 - Implementation | 6
16 | Phase 4 - Manufacturing | 6
17 | Phase 1 - Planning | 26
17 | Phase 2 - Initiation | 12
17 | Phase 3 - Implementation | 25
17 | Phase 4 - Manufacturing | 12
18 | Phase 1 - Planning | 8
18 | Phase 2 - Initiation | 13
18 | Phase 3 - Implementation | 13
18 | Phase 4 - Manufacturing | 28
19 | Phase 1 - Planning | 27
19 | Phase 2 - Initiation | 21
19 | Phase 3 - Implementation | 16
19 | Phase 4 - Manufacturing | 18
20 | Phase 1 - Planning | 7
20 | Phase 2 - Initiation | 22
20 | Phase 3 - Implementation | 24
20 | Phase 4 - Manufacturing | 26
21 | Phase 1 - Planning | 7
21 | Phase 2 - Initiation | 18
21 | Phase 3 - Implementation | 23
21 | Phase 4 - Manufacturing | 11
22 | Phase 1 - Planning | 4
22 | Phase 2 - Initiation | 3
22 | Phase 3 - Implementation | 6
22 | Phase 4 - Manufacturing | 27
23 | Phase 1 - Planning | 6
23 | Phase 2 - Initiation | 25
23 | Phase 3 - Implementation | 3
23 | Phase 4 - Manufacturing | 18
24 | Phase 1 - Planning | 12
24 | Phase 2 - Initiation | 19
24 | Phase 3 - Implementation | 21
24 | Phase 4 - Manufacturing | 20
25 | Phase 1 - Planning | 10
25 | Phase 2 - Initiation | 9
25 | Phase 3 - Implementation | 6
25 | Phase 4 - Manufacturing | 5
26 | Phase 1 - Planning | 27
26 | Phase 2 - Initiation | 3
26 | Phase 3 - Implementation | 23
26 | Phase 4 - Manufacturing | 6
27 | Phase 1 - Planning | 22
27 | Phase 2 - Initiation | 11
27 | Phase 3 - Implementation | 19
27 | Phase 4 - Manufacturing | 18
28 | Phase 1 - Planning | 14
28 | Phase 2 - Initiation | 6
28 | Phase 3 - Implementation | 15
28 | Phase 4 - Manufacturing | 30
29 | Phase 1 - Planning | 7
29 | Phase 2 - Initiation | 4
29 | Phase 3 - Implementation | 4
29 | Phase 4 - Manufacturing | 15
30 | Phase 1 - Planning | 20
30 | Phase 2 - Initiation | 11
30 | Phase 3 - Implementation | 7
30 | Phase 4 - Manufacturing | 23
31 | Phase 1 - Planning | 4
31 | Phase 2 - Initiation | 18
31 | Phase 3 - Implementation | 17
31 | Phase 4 - Manufacturing | 22
32 | Phase 1 - Planning | 9
32 | Phase 2 - Initiation | 4
32 | Phase 3 - Implementation | 24
32 | Phase 4 - Manufacturing | 8
33 | Phase 1 - Planning | 11
33 | Phase 2 - Initiation | 20
33 | Phase 3 - Implementation | 4
33 | Phase 4 - Manufacturing | 10
34 | Phase 1 - Planning | 11
34 | Phase 2 - Initiation | 20
34 | Phase 3 - Implementation | 14
34 | Phase 4 - Manufacturing | 23
35 | Phase 1 - Planning | 23
35 | Phase 2 - Initiation | 16
35 | Phase 3 - Implementation | 10
35 | Phase 4 - Manufacturing | 26
36 | Phase 1 - Planning | 8
36 | Phase 2 - Initiation | 3
36 | Phase 3 - Implementation | 23
36 | Phase 4 - Manufacturing | 23
37 | Phase 1 - Planning | 6
37 | Phase 2 - Initiation | 10
37 | Phase 3 - Implementation | 32
37 | Phase 4 - Manufacturing | 7
38 | Phase 1 - Planning | 13
38 | Phase 2 - Initiation | 22
38 | Phase 3 - Implementation | 20
38 | Phase 4 - Manufacturing | 5
39 | Phase 1 - Planning | 27
39 | Phase 2 - Initiation | 18
39 | Phase 3 - Implementation | 10
39 | Phase 4 - Manufacturing | 9
40 | Phase 1 - Planning | 26
40 | Phase 2 - Initiation | 17
40 | Phase 3 - Implementation | 19
40 | Phase 4 - Manufacturing | 15
41 | Phase 1 - Planning | 28
41 | Phase 2 - Initiation | 28
41 | Phase 3 - Implementation | 20
41 | Phase 4 - Manufacturing | 6
42 | Phase 1 - Planning | 9
42 | Phase 2 - Initiation | 26
42 | Phase 3 - Implementation | 11
42 | Phase 4 - Manufacturing | 21
43 | Phase 1 - Planning | 14
43 | Phase 2 - Initiation | 7
43 | Phase 3 - Implementation | 6
43 | Phase 4 - Manufacturing | 6
44 | Phase 1 - Planning | 8
44 | Phase 2 - Initiation | 5
44 | Phase 3 - Implementation | 10
44 | Phase 4 - Manufacturing | 22
45 | Phase 1 - Planning | 12
45 | Phase 2 - Initiation | 9
45 | Phase 3 - Implementation | 26
45 | Phase 4 - Manufacturing | 25
46 | Phase 1 - Planning | 16
46 | Phase 2 - Initiation | 18
46 | Phase 3 - Implementation | 31
46 | Phase 4 - Manufacturing | 6
47 | Phase 1 - Planning | 29
47 | Phase 2 - Initiation | 22
47 | Phase 3 - Implementation | 27
47 | Phase 4 - Manufacturing | 9
48 | Phase 1 - Planning | 21
48 | Phase 2 - Initiation | 26
48 | Phase 3 - Implementation | 10
48 | Phase 4 - Manufacturing | 32
49 | Phase 1 - Planning | 31
49 | Phase 2 - Initiation | 26
49 | Phase 3 - Implementation | 29
49 | Phase 4 - Manufacturing | 21
50 | Phase 1 - Planning | 11
50 | Phase 2 - Initiation | 23
50 | Phase 3 - Implementation | 19
50 | Phase 4 - Manufacturing | 9
51 | Phase 1 - Planning | 11
51 | Phase 2 - Initiation | 5
51 | Phase 3 - Implementation | 6
51 | Phase 4 - Manufacturing | 24
52 | Phase E - Deployment | 4
52 | Phase C - Development | 22
52 | Phase A - Initiation | 23
52 | Phase F - Post-deployment | 7
52 | Phase B - Preparation | 21
52 | Phase D - Testing | 23
53 | Phase E - Deployment | 27
53 | Phase C - Development | 8
53 | Phase A - Initiation | 9
53 | Phase F - Post-deployment | 24
53 | Phase B - Preparation | 27
53 | Phase D - Testing | 19
54 | Phase E - Deployment | 11
54 | Phase C - Development | 4
54 | Phase A - Initiation | 9
54 | Phase F - Post-deployment | 17
54 | Phase B - Preparation | 27
54 | Phase D - Testing | 14
55 | Phase E - Deployment | 24
55 | Phase C - Development | 9
55 | Phase A - Initiation | 27
55 | Phase F - Post-deployment | 6
55 | Phase B - Preparation | 6
55 | Phase D - Testing | 6
56 | Phase E - Deployment | 4
56 | Phase C - Development | 4
56 | Phase A - Initiation | 8
56 | Phase F - Post-deployment | 4
56 | Phase B - Preparation | 28
56 | Phase D - Testing | 15
57 | Phase E - Deployment | 24
57 | Phase C - Development | 13
57 | Phase A - Initiation | 12
57 | Phase F - Post-deployment | 4
57 | Phase B - Preparation | 7
57 | Phase D - Testing | 8
58 | Phase E - Deployment | 3
58 | Phase C - Development | 11
58 | Phase A - Initiation | 20
58 | Phase F - Post-deployment | 26
58 | Phase B - Preparation | 24
58 | Phase D - Testing | 22
59 | Phase E - Deployment | 29
59 | Phase C - Development | 25
59 | Phase A - Initiation | 6
59 | Phase F - Post-deployment | 9
59 | Phase B - Preparation | 5
59 | Phase D - Testing | 13
60 | Phase E - Deployment | 28
60 | Phase C - Development | 16
60 | Phase A - Initiation | 12
60 | Phase F - Post-deployment | 27
60 | Phase B - Preparation | 10
60 | Phase D - Testing | 8
61 | Phase E - Deployment | 12
61 | Phase C - Development | 22
61 | Phase A - Initiation | 24
61 | Phase F - Post-deployment | 25
61 | Phase B - Preparation | 8
61 | Phase D - Testing | 2
62 | Phase E - Deployment | 17
62 | Phase C - Development | 7
62 | Phase A - Initiation | 4
62 | Phase F - Post-deployment | 11
62 | Phase B - Preparation | 5
62 | Phase D - Testing | 14
63 | Phase E - Deployment | 9
63 | Phase C - Development | 14
63 | Phase A - Initiation | 17
63 | Phase F - Post-deployment | 13
63 | Phase B - Preparation | 9
63 | Phase D - Testing | 15
64 | Phase E - Deployment | 21
64 | Phase C - Development | 23
64 | Phase A - Initiation | 3
64 | Phase F - Post-deployment | 23
64 | Phase B - Preparation | 23
64 | Phase D - Testing | 27
65 | Phase E - Deployment | 25
65 | Phase C - Development | 9
65 | Phase A - Initiation | 12
65 | Phase F - Post-deployment | 17
65 | Phase B - Preparation | 25
65 | Phase D - Testing | 10
66 | Phase E - Deployment | 16
66 | Phase C - Development | 27
66 | Phase A - Initiation | 20
66 | Phase F - Post-deployment | 26
66 | Phase B - Preparation | 11
66 | Phase D - Testing | 20
67 | Phase E - Deployment | 26
67 | Phase C - Development | 14
67 | Phase A - Initiation | 32
67 | Phase F - Post-deployment | 6
67 | Phase B - Preparation | 16
67 | Phase D - Testing | 23
68 | Phase E - Deployment | 3
68 | Phase C - Development | 9
68 | Phase A - Initiation | 4
68 | Phase F - Post-deployment | 20
68 | Phase B - Preparation | 13
68 | Phase D - Testing | 4
69 | Phase E - Deployment | 22
69 | Phase C - Development | 4
69 | Phase A - Initiation | 14
69 | Phase F - Post-deployment | 31
69 | Phase B - Preparation | 27
69 | Phase D - Testing | 15
70 | Phase E - Deployment | 5
70 | Phase C - Development | 17
70 | Phase A - Initiation | 18
70 | Phase F - Post-deployment | 29
70 | Phase B - Preparation | 7
70 | Phase D - Testing | 3
71 | Phase E - Deployment | 17
71 | Phase C - Development | 28
71 | Phase A - Initiation | 26
71 | Phase F - Post-deployment | 13
71 | Phase B - Preparation | 16
71 | Phase D - Testing | 12
72 | Phase E - Deployment | 28
72 | Phase C - Development | 18
72 | Phase A - Initiation | 30
72 | Phase F - Post-deployment | 3
72 | Phase B - Preparation | 22
72 | Phase D - Testing | 9
73 | Phase E - Deployment | 6
73 | Phase C - Development | 3
73 | Phase A - Initiation | 20
73 | Phase F - Post-deployment | 16
73 | Phase B - Preparation | 8
73 | Phase D - Testing | 11
74 | Phase E - Deployment | 7
74 | Phase C - Development | 11
74 | Phase A - Initiation | 25
74 | Phase F - Post-deployment | 32
74 | Phase B - Preparation | 9
74 | Phase D - Testing | 6
75 | Phase E - Deployment | 8
75 | Phase C - Development | 19
75 | Phase A - Initiation | 3
75 | Phase F - Post-deployment | 26
75 | Phase B - Preparation | 31
75 | Phase D - Testing | 26
76 | Phase E - Deployment | 14
76 | Phase C - Development | 15
76 | Phase A - Initiation | 13
76 | Phase F - Post-deployment | 29
76 | Phase B - Preparation | 25
76 | Phase D - Testing | 7
77 | Phase E - Deployment | 19
77 | Phase C - Development | 14
77 | Phase A - Initiation | 5
77 | Phase F - Post-deployment | 11
77 | Phase B - Preparation | 20
77 | Phase D - Testing | 17
78 | Phase E - Deployment | 8
78 | Phase C - Development | 21
78 | Phase A - Initiation | 27
78 | Phase F - Post-deployment | 11
78 | Phase B - Preparation | 9
78 | Phase D - Testing | 9
79 | Phase E - Deployment | 2
79 | Phase C - Development | 14
79 | Phase A - Initiation | 9
79 | Phase F - Post-deployment | 15
79 | Phase B - Preparation | 17
79 | Phase D - Testing | 9
80 | Phase E - Deployment | 8
80 | Phase C - Development | 7
80 | Phase A - Initiation | 4
80 | Phase F - Post-deployment | 2
80 | Phase B - Preparation | 9
80 | Phase D - Testing | 18
81 | Phase E - Deployment | 17
81 | Phase C - Development | 1
81 | Phase A - Initiation | 8
81 | Phase F - Post-deployment | 21
81 | Phase B - Preparation | 11
81 | Phase D - Testing | 17
82 | Phase E - Deployment | 14
82 | Phase C - Development | 19
82 | Phase A - Initiation | 13
82 | Phase F - Post-deployment | 16
82 | Phase B - Preparation | 18
82 | Phase D - Testing | 3
83 | Phase E - Deployment | 13
83 | Phase C - Development | 14
83 | Phase A - Initiation | 12
83 | Phase F - Post-deployment | 4
83 | Phase B - Preparation | 12
83 | Phase D - Testing | 17
84 | Phase E - Deployment | 9
84 | Phase C - Development | 17
84 | Phase A - Initiation | 5
84 | Phase F - Post-deployment | 7
84 | Phase B - Preparation | 6
84 | Phase D - Testing | 5
85 | Phase E - Deployment | 16
85 | Phase C - Development | 18
85 | Phase A - Initiation | 14
85 | Phase F - Post-deployment | 15
85 | Phase B - Preparation | 3
85 | Phase D - Testing | 18
86 | Phase E - Deployment | 4
86 | Phase C - Development | 20
86 | Phase A - Initiation | 10
86 | Phase F - Post-deployment | 2
86 | Phase B - Preparation | 7
86 | Phase D - Testing | 6
87 | Phase E - Deployment | 11
87 | Phase C - Development | 9
87 | Phase A - Initiation | 4
87 | Phase F - Post-deployment | 14
87 | Phase B - Preparation | 12
87 | Phase D - Testing | 17
88 | Phase E - Deployment | 14
88 | Phase C - Development | 7
88 | Phase A - Initiation | 26
88 | Phase F - Post-deployment | 20
88 | Phase B - Preparation | 26
88 | Phase D - Testing | 6
89 | Phase E - Deployment | 14
89 | Phase C - Development | 20
89 | Phase A - Initiation | 17
89 | Phase F - Post-deployment | 10
89 | Phase B - Preparation | 9
89 | Phase D - Testing | 19
90 | Phase E - Deployment | 27
90 | Phase C - Development | 9
90 | Phase A - Initiation | 3
90 | Phase F - Post-deployment | 22
90 | Phase B - Preparation | 4
90 | Phase D - Testing | 20
91 | Phase E - Deployment | 32
91 | Phase C - Development | 16
91 | Phase A - Initiation | 6
91 | Phase F - Post-deployment | 17
91 | Phase B - Preparation | 23
91 | Phase D - Testing | 25
92 | Phase E - Deployment | 15
92 | Phase C - Development | 6
92 | Phase A - Initiation | 12
92 | Phase F - Post-deployment | 14
92 | Phase B - Preparation | 20
92 | Phase D - Testing | 26
93 | Phase E - Deployment | 26
93 | Phase C - Development | 9
93 | Phase A - Initiation | 8
93 | Phase F - Post-deployment | 10
93 | Phase B - Preparation | 26
93 | Phase D - Testing | 13
94 | Phase E - Deployment | 7
94 | Phase C - Development | 25
94 | Phase A - Initiation | 22
94 | Phase F - Post-deployment | 5
94 | Phase B - Preparation | 29
94 | Phase D - Testing | 10
95 | Phase E - Deployment | 17
95 | Phase C - Development | 27
95 | Phase A - Initiation | 20
95 | Phase F - Post-deployment | 16
95 | Phase B - Preparation | 29
95 | Phase D - Testing | 18
96 | Phase E - Deployment | 21
96 | Phase C - Development | 14
96 | Phase A - Initiation | 22
96 | Phase F - Post-deployment | 8
96 | Phase B - Preparation | 13
96 | Phase D - Testing | 28
97 | Phase E - Deployment | 23
97 | Phase C - Development | 8
97 | Phase A - Initiation | 3
97 | Phase F - Post-deployment | 7
97 | Phase B - Preparation | 26
97 | Phase D - Testing | 5
98 | Phase E - Deployment | 12
98 | Phase C - Development | 14
98 | Phase A - Initiation | 26
98 | Phase F - Post-deployment | 19
98 | Phase B - Preparation | 25
98 | Phase D - Testing | 8
99 | Phase E - Deployment | 19
99 | Phase C - Development | 9
99 | Phase A - Initiation | 22
99 | Phase F - Post-deployment | 5
99 | Phase B - Preparation | 14
99 | Phase D - Testing | 27
100 | Phase E - Deployment | 15
100 | Phase C - Development | 19
100 | Phase A - Initiation | 16
100 | Phase F - Post-deployment | 18
100 | Phase B - Preparation | 14
100 | Phase D - Testing | 4
101 | Phase E - Deployment | 5
101 | Phase C - Development | 18
101 | Phase A - Initiation | 21
101 | Phase F - Post-deployment | 9
101 | Phase B - Preparation | 29
101 | Phase D - Testing | 5
102 | Phase E - Deployment | 12
102 | Phase C - Development | 13
102 | Phase A - Initiation | 9
102 | Phase F - Post-deployment | 5
102 | Phase B - Preparation | 1
102 | Phase D - Testing | 24
103 | Phase E - Deployment | 19
103 | Phase C - Development | 1
103 | Phase A - Initiation | 2
103 | Phase F - Post-deployment | 23
103 | Phase B - Preparation | 5
103 | Phase D - Testing | 12
104 | Phase 1 - Planning | 21
104 | Phase 2 - Initiation | 27
104 | Phase 3 - Implementation | 17
104 | Phase 4 - Manufacturing | 4

## Projects_Locations
In this tab are the projects country locations
Project ID | Country
1 | Equateur
2 | France
3 | Liban
4 | Egypte
5 | Afrique du Sud
6 | Albanie
7 | Hollande
8 | Allemagne
9 | Belgique
10 | Benin
11 | Italie
12 | Hongrie
13 | France
14 | Croatie
15 | Burkina Faso
16 | Cote d'Ivoire
17 | Espagne
18 | Gabon
19 | Republique Chèque
20 | Colombie
21 | Estonie
22 | Bresil
23 | Suisse
24 | Ukraine
25 | Togo
26 | Allemagne
27 | La Reunion
28 | Russie
29 | Belgique
30 | Canada
31 | Norvege
32 | Turquie
33 | Malte
34 | Israel
35 | Norvege
36 | Portugal
37 | Pologne
38 | Grece
39 | Danemark
40 | Senegal
41 | Slovaquie
42 | Lituanie
43 | Luxembourg
44 | Jordanie
45 | Gambie
46 | Macedoine
47 | Niger
48 | Slovenie
49 | Ile Maurice
50 | Serbie
51 | Suede
52 | France
53 | Belgique
54 | Hollande
55 | Luxembourg
56 | Italie
57 | Japon
58 | Espagne
59 | Hongrie
60 | Pologne
61 | Republique Chèque
62 | Slovaquie
63 | Allemagne
64 | Serbie
65 | Croatie
66 | Slovenie
67 | Macedoine
68 | Albanie
69 | Chine
70 | Malte
71 | Turquie
72 | Grece
73 | Portugal
74 | Ukraine
75 | Russie
76 | Bielorussie
77 | Lituanie
78 | Estonie
79 | Suede
80 | Danemark
81 | Norvege
82 | Suisse
83 | Cote d'Ivoire
84 | Chine
85 | Afrique du Sud
86 | France
87 | Serbie
88 | Turquie
89 | Grece
90 | Afrique du Sud
91 | Canada
92 | Pologne
93 | Danemark
94 | Israel
95 | Japon
96 | Chine
97 | Japon
98 | Japon
99 | Indonesie
100 | Malaysie
101 | Chine
102 | Ile Maurice
103 | La Reunion
104 | Bielorussie

## Country_Profiles
In this tab are the countries region, and the type of the local entity
Country | Region | Type
France | Western Europe | Affiliate
Belgique | Western Europe | Affiliate
Hollande | Western Europe | Affiliate
Luxembourg | Western Europe | Affiliate
Italie | Western Europe | Affiliate
Japon | Asia Pacific | Affiliate
Espagne | Western Europe | Affiliate
Hongrie | Central/Eastern Europe-Middle East-Africa | Affiliate
Pologne | Central/Eastern Europe-Middle East-Africa | Affiliate
Republique Chèque | Central/Eastern Europe-Middle East-Africa | Affiliate
Slovaquie | Central/Eastern Europe-Middle East-Africa | Affiliate
Allemagne | Western Europe | Affiliate
Serbie | Central/Eastern Europe-Middle East-Africa | Affiliate
Croatie | Central/Eastern Europe-Middle East-Africa | Affiliate
Slovenie | Central/Eastern Europe-Middle East-Africa | Affiliate
Macedoine | Central/Eastern Europe-Middle East-Africa | Distributor
Albanie | Central/Eastern Europe-Middle East-Africa | Distributor
Canada | North and Latin America | Distributor
Malte | Central/Eastern Europe-Middle East-Africa | Distributor
Turquie | Central/Eastern Europe-Middle East-Africa | Distributor
Grece | Western Europe | Affiliate
Portugal | Western Europe | Distributor
Ukraine | Central/Eastern Europe-Middle East-Africa | Affiliate
Russie | Central/Eastern Europe-Middle East-Africa | Affiliate
Bielorussie | Central/Eastern Europe-Middle East-Africa | Distributor
Lituanie | Central/Eastern Europe-Middle East-Africa | Affiliate
Estonie | Central/Eastern Europe-Middle East-Africa | Affiliate
Suede | Western Europe | Distributor
Danemark | Western Europe | Distributor
Norvege | Western Europe | Distributor
Suisse | Western Europe | Affiliate
Cote d'Ivoire | Central/Eastern Europe-Middle East-Africa | Distributor
Senegal | Central/Eastern Europe-Middle East-Africa | Distributor
Afrique du Sud | Central/Eastern Europe-Middle East-Africa | Distributor
Gambie | Central/Eastern Europe-Middle East-Africa | Distributor
Gabon | Central/Eastern Europe-Middle East-Africa | Distributor
Benin | Central/Eastern Europe-Middle East-Africa | Distributor
Togo | Central/Eastern Europe-Middle East-Africa | Distributor
Burkina Faso | Central/Eastern Europe-Middle East-Africa | Distributor
Niger | Central/Eastern Europe-Middle East-Africa | Distributor
Liban | Central/Eastern Europe-Middle East-Africa | Distributor
Jordanie | Central/Eastern Europe-Middle East-Africa | Distributor
Israel | Central/Eastern Europe-Middle East-Africa | Distributor
Egypte | Central/Eastern Europe-Middle East-Africa | Distributor
Colombie | North and Latin America | Distributor
Bresil | North and Latin America | Distributor
Equateur | North and Latin America | Affiliate
Indonesie | Asia Pacific | Distributor
Malaysie | Asia Pacific | Affiliate
Chine | Asia Pacific | Distributor
Ile Maurice | Central/Eastern Europe-Middle East-Africa | Distributor
La Reunion | Central/Eastern Europe-Middle East-Africa | Affiliate